## Instructions
Estimate Add-in Demonstration
Paul A. Jensen
| • | The models in this section were created by the Estimate add-in. To use them you must install the Estimate add-in using the Add-ins Command on the Tools menu of Excel. To insure that functions are active choose the Links command from the Estimate menu. Click the Link Functions command. Click OK to replace the functions on all worksheets.
| • | Use the Actions Command on the Estimate menu to operate on existing models. Use the New Estimate command to create new models.
| • | Only models that include uncertainty, have user-defined functions. A user-defined function is linked to the add-in on the computer that created the function. If not frozen, the workbook will display a message when opened on another computer.
| • | Models that include uncertainty can be frozen to replace functions with their numerical values. If not frozen, the workbook will display a message when opened on another computer.
| • | If the workbook is to be opened on a different computer, choose the Links command. Then click the Freeze Functions button. All user-defined functions are replaced with their numeric values. The workbook is said to be frozen. User-defined functions are no longer active.
| • | If you use functions in cells outside the forms created by the add-in, these functions are not affected by the Links command. Use the Links command under the Edit menu to correct these links.
Instructions |  | http://www.me.utexas.edu/~jensen/ORMM/omie/computation/unit/estimate/index.html
Estimate Add-in
Topic
Line 1 |  | A line with a two levels in the Work Breakdown Stucture (WBS)
Line 2 |  | A line with a three levels in the Work Breakdown Stucture (WBS)
Line 3 |  | A line with a four levels in the Work Breakdown Stucture (WBS)
Time |  | Costs specified over time
Distribution |  | Costs uncertain and specified by a distribution
CBS |  | Cost estimating with a Cost Breakdown Structure (CBS)
CBS-Time |  | Cost estimating with a Cost Breakdown Structure over time

## A_Line1
Capital Budget: A_Line1
|  | Work Breakdown Structure |  |  | Summary |  |  | Estimate
|  | Level 1:A_Line1 |  | WP | Level 2 |  |  | Level 1:A_Line1
|  | L2 | Description | Cost | Index | Description | Cost | Cost
| 1 | 0 | Assembly Line | 0 | 0 | Assembly Line | 0 | 308000
| 2 | 1 | Process design | 14000 | 1 | Process design | 14000
| 3 | 2 | Capacity Planning | 23000 | 2 | Capacity Planning | 23000
| 4 | 3 | Material handling | 11000 | 3 | Material handling | 11000
| 5 | 4 | Facilities planning | 17000 | 4 | Facilities planning | 17000
| 6 | 5 | Purchasing | 107000 | 5 | Purchasing | 107000
| 7 | 6 | Development of training | 18000 | 6 | Development of training | 18000
| 8 | 7 | Actual training | 51000 | 7 | Actual training | 51000
| 9 | 8 | Installation and Integration | 32000 | 8 | Installation and Integration | 32000
| 10 | 9 | Management of Project | 35000 | 9 | Management of Project | 35000
| 11 | 10 | Finish | 0 | 10 | Finish | 0
|  |  | Total | 308000

## A_Line2
Capital Budget: A_Line2
Work Breakdown Structure
|  | Level 1:A_Line2 |  |  | WP
|  | L2 | L3 | Description | Cost
| 1 | 0 | 0 | Assembly line | 0
| 2 | 1 | 0 | Process design | 0
| 3 | 1 | 1 | Develop list of assembly operations | 1880
| 4 | 1 | 2 | Estimate assembly time for each operation | 3460
| 5 | 1 | 3 | Assign operations to workstations | 1780
| 6 | 1 | 4 | Design of equipment required at each station | 7220
| 7 | 2 | 0 | Capacity Planning
| 8 | 2 | 1 | Forecast of future demand | 1780
| 9 | 2 | 2 | Estimates of required assembly rates | 1880
| 10 | 2 | 3 | Design of equipment required at each station | 17800
| 11 | 2 | 4 | Estimate of labor requirements | 1780
| 12 | 3 | 0 | Material handling
| 13 | 3 | 1 | Design of line layout | 5540
| 14 | 3 | 2 | Selection of material handling equipment | 3560
| 15 | 3 | 3 | Integration design for the material-handling system | 1980
| 16 | 4 | 0 | Facilities planning
| 17 | 4 | 1 | Determination of space requirements | 5440
| 18 | 4 | 2 | Analysis of energy requirements | 1980
| 19 | 4 | 3 | Temperature and humidity analysis | 3660
| 20 | 4 | 4 | Facility and integration design of the whole line | 5540
| 21 | 5 | 0 | Purchasing
| 22 | 5 | 1 | Equipment | 43360
| 23 | 5 | 2 | Material handling system | 35040
| 24 | 5 | 3 | Assembly machines | 28400
| 25 | 6 | 0 | Development of training
| 26 | 6 | 1 | For assembly line operators | 6040
| 27 | 6 | 2 | For quality control personnel | 6040
| 28 | 6 | 3 | For foremen and managers | 6040
| 29 | 7 | 0 | Actual training
| 30 | 7 | 1 | Assembly line operators | 17100
| 31 | 7 | 2 | Quality control personnel | 17100
| 32 | 7 | 3 | Foremen and managers | 17100
| 33 | 8 | 0 | Installation and Integration
| 34 | 8 | 1 | Shipment of equipment and machines | 7040
| 35 | 8 | 2 | Installations | 12080
| 36 | 8 | 3 | Testing of components | 6040
| 37 | 8 | 4 | Integration and testing of line | 3660
| 38 | 8 | 5 | Operations | 3660
| 39 | 9 | 0 | Management of Project
| 40 | 9 | 1 | Design and planning | 17300
| 41 | 9 | 2 | Implementation monitoring and control | 17300
| 42 | 10 | 0 | Finish | 0

## A_Line3
Capital Budget: A_Line3
|  | Work Breakdown Structure |  |  |  |  | Summary |  |  | Estimate
|  | Level 1:A_Line3 |  |  |  | WP | Level 2 |  |  | Level 1:A_Line3
|  | L2 | L3 | L4 | Description | Cost | Index | Description | Cost | Cost
| 1 | 0 | 0 | 0 | Assembly line | 0 | 0 | Assembly line | 0 | 308580
| 2 | 1 | 0 | 0 | Process design | 0 | 1 | Process design | 14340
| 3 | 1 | 1 | 0 | Develop list of assembly operations | 0 | 2 | Capacity Planning | 23240
| 4 | 1 | 1 | 1 | Labor | 1200 | 3 | Material handling | 11080
| 5 | 1 | 1 | 2 | Materials | 200 | 4 | Facilities planning | 16620
| 6 | 1 | 1 | 3 | Overhead | 480 | 5 | Purchasing | 106800
| 7 | 1 | 2 | 0 | Estimate assembly time for each operation | 0 | 6 | Development of training | 18120
| 8 | 1 | 2 | 1 | Labor | 2400 | 7 | Actual training | 51300
| 9 | 1 | 2 | 2 | Materials | 100 | 8 | Installation and Integration | 32480
| 10 | 1 | 2 | 3 | Overhead | 960 | 9 | Management of Project | 34600
| 11 | 1 | 3 | 0 | Assign operations to workstations | 0 | 10 | Finish | 0
| 12 | 1 | 3 | 1 | Labor | 1200
| 13 | 1 | 3 | 2 | Materials | 100
| 14 | 1 | 3 | 3 | Overhead | 480
| 15 | 1 | 4 | 0 | Design of equipment required at each station | 0
| 16 | 1 | 4 | 1 | Labor | 4800
| 17 | 1 | 4 | 2 | Materials | 500
| 18 | 1 | 4 | 3 | Overhead | 1920
| 19 | 2 | 0 | 0 | Capacity Planning | 0
| 20 | 2 | 1 | 0 | Forecase of future demand | 0
| 21 | 2 | 1 | 1 | Labor | 1200
| 22 | 2 | 1 | 2 | Materials | 100
| 23 | 2 | 1 | 3 | Overhead | 480
| 24 | 2 | 2 | 0 | Estimates of required assembly rates | 0
| 25 | 2 | 2 | 1 | Labor | 1200
| 26 | 2 | 2 | 2 | Materials | 200
| 27 | 2 | 2 | 3 | Overhead | 480
| 28 | 2 | 3 | 0 | Design of equipment required at each station | 0
| 29 | 2 | 3 | 1 | Labor | 12000
| 30 | 2 | 3 | 2 | Materials | 1000
| 31 | 2 | 3 | 3 | Overhead | 4800
| 32 | 2 | 4 | 0 | Estimate of labor requirements | 0
| 33 | 2 | 4 | 1 | Labor | 1200
| 34 | 2 | 4 | 2 | Materials | 100
| 35 | 2 | 4 | 3 | Overhead | 480
| 36 | 3 | 0 | 0 | Material handling | 0
| 37 | 3 | 1 | 0 | Design of line layout | 0
| 38 | 3 | 1 | 1 | Labor | 3600
| 39 | 3 | 1 | 2 | Materials | 500
| 40 | 3 | 1 | 3 | Overhead | 1440
| 41 | 3 | 2 | 0 | Selection of material handling equipment | 0
| 42 | 3 | 2 | 1 | Labor | 2400
| 43 | 3 | 2 | 2 | Materials | 200
| 44 | 3 | 2 | 3 | Overhead | 960
| 45 | 3 | 3 | 0 | Integration design for the material-handling system | 0
| 46 | 3 | 3 | 1 | Labor | 1200
| 47 | 3 | 3 | 2 | Materials | 300
| 48 | 3 | 3 | 3 | Overhead | 480
| 49 | 4 | 0 | 0 | Facilities planning | 0
| 50 | 4 | 1 | 0 | Determination of space requirements | 0
| 51 | 4 | 1 | 1 | Labor | 3600
| 52 | 4 | 1 | 2 | Materials | 400
| 53 | 4 | 1 | 3 | Overhead | 1440
| 54 | 4 | 2 | 0 | Analysis of energy requirements | 0
| 55 | 4 | 2 | 1 | Labor | 1200
| 56 | 4 | 2 | 2 | Materials | 300
| 57 | 4 | 2 | 3 | Overhead | 480
| 58 | 4 | 3 | 0 | Temperature and humidity analysis | 0
| 59 | 4 | 3 | 1 | Labor | 2400
| 60 | 4 | 3 | 2 | Materials | 300
| 61 | 4 | 3 | 3 | Overhead | 960
| 62 | 4 | 4 | 0 | Facility and integration design of the whole line | 0
| 63 | 4 | 4 | 1 | Labor | 3600
| 64 | 4 | 4 | 2 | Materials | 500
| 65 | 4 | 4 | 3 | Overhead | 1440
| 66 | 5 | 0 | 1 | Purchasing | 0
| 67 | 5 | 1 | 0 | Equipment | 0
| 68 | 5 | 1 | 1 | Labor | 2400
| 69 | 5 | 1 | 2 | Materials | 40000
| 70 | 5 | 1 | 3 | Overhead | 960
| 71 | 5 | 2 | 0 | Material handling system | 0
| 72 | 5 | 2 | 1 | Labor | 3600
| 73 | 5 | 2 | 2 | Material | 30000
| 74 | 5 | 2 | 3 | Overhead | 1440
| 75 | 5 | 3 | 0 | Assembly machines | 0
| 76 | 5 | 3 | 1 | Labor | 6000
| 77 | 5 | 3 | 2 | Material | 20000
| 78 | 5 | 3 | 3 | Overhead | 2400
| 79 | 6 | 0 | 0 | Development of training | 0
| 80 | 6 | 1 | 0 | For assembly line operators | 0
| 81 | 6 | 2 | 1 | Labor | 3600
| 82 | 6 | 2 | 2 | Materials | 1000
| 83 | 6 | 2 | 3 | Overhead | 1440
| 84 | 6 | 2 | 0 | For quality control personnel | 0
| 85 | 6 | 2 | 1 | Labor | 3600
| 86 | 6 | 2 | 2 | Materials | 1000
| 87 | 6 | 2 | 3 | Overhead | 1440
| 88 | 6 | 3 | 0 | For foremen and managers | 0
| 89 | 6 | 2 | 1 | Labor | 3600
| 90 | 6 | 2 | 2 | Materials | 1000
| 91 | 6 | 2 | 3 | Overhead | 1440
| 92 | 7 | 0 | 0 | Actual training | 0
| 93 | 7 | 1 | 0 | Assembly line operators | 0
| 94 | 7 | 2 | 1 | Labor | 12000
| 95 | 7 | 2 | 2 | Materials | 300
| 96 | 7 | 2 | 3 | Overhead | 4800
| 97 | 7 | 2 | 0 | Quality control personnel | 0
| 98 | 7 | 2 | 1 | Labor | 12000
| 99 | 7 | 2 | 2 | Materials | 300
| 100 | 7 | 2 | 3 | Overhead | 4800
| 101 | 7 | 3 | 0 | Foremen and managers | 0
| 102 | 7 | 3 | 1 | Labor | 12000
| 103 | 7 | 3 | 2 | Materials | 300
| 104 | 7 | 3 | 3 | Overhead | 4800
| 105 | 8 | 0 | 0 | Installation and Integration | 0
| 106 | 8 | 1 | 0 | Shipment of equipment and machines | 0
| 107 | 8 | 1 | 1 | Labor | 3600
| 108 | 8 | 1 | 2 | Materials | 2000
| 109 | 8 | 1 | 3 | Overhead | 1440
| 110 | 8 | 2 | 0 | Installations | 0
| 111 | 8 | 2 | 1 | Labor | 7200
| 112 | 8 | 2 | 2 | Materials | 2000
| 113 | 8 | 2 | 3 | Overhead | 2880
| 114 | 8 | 3 | 0 | Testing of components | 0
| 115 | 8 | 3 | 1 | Labor | 3600
| 116 | 8 | 3 | 2 | Materials | 1000
| 117 | 8 | 3 | 3 | Overhead | 1440
| 118 | 8 | 4 | 0 | Integration and testing of line | 0
| 119 | 8 | 4 | 1 | Labor | 2400
| 120 | 8 | 4 | 2 | Materials | 300
| 121 | 8 | 4 | 3 | Overhead | 960
| 122 | 8 | 5 | 0 | Operations | 0
| 123 | 8 | 5 | 1 | Labor | 2400
| 124 | 8 | 5 | 2 | Materials | 300
| 125 | 8 | 5 | 3 | Overhead | 960
| 126 | 9 | 0 | 0 | Management of Project | 0
| 127 | 9 | 1 | 0 | Design and planning | 0
| 128 | 9 | 1 | 1 | Labor | 12000
| 129 | 9 | 1 | 2 | Materials | 500
| 130 | 9 | 1 | 3 | Overhead | 4800
| 131 | 9 | 2 | 0 | Implementation monitoring and control | 0
| 132 | 9 | 2 | 1 | Labor | 12000
| 133 | 9 | 2 | 2 | Materials | 500
| 134 | 9 | 2 | 3 | Overhead | 4800
| 135 | 10 | 0 | 0 | Finish | 0

## A_Line1_Time
Capital Budget: A_Line1_Time
Time/Cost
|  | Work Breakdown Structure |  |  | Schedule |  |  | Rate | 2% | [6 empty] | Summary |  |  | Estimate
|  | Level 1:A_Line1_Time |  | WP |  |  | Time | 0 | 1 | 2 | 3 | 4 | 5 | 6 | NPW | Level 2 |  | NPW | Level 1:A_Line1_Time
|  | L2 | Description | Cost | Start | Finish | P/F | 1 | 0.98039 | 0.96117 | 0.94232 | 0.92385 | 0.90573 | 0.88797 | Cost | Index | Description | Cost | NPW Cost
| 1 | 0 | Assembly Line | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Assembly Line | 0 | 288626.7294
| 2 | 1 | Process design | 14000 | 1 | 2 |  | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 13590.9266 | 1 | Process design | 13590.9266
| 3 | 2 | Capacity Planning | 23000 | 1 | 3 |  | 0 | 0.33333 | 0.33333 | 0.33333 | 0 | 0 | 0 | 22109.7718 | 2 | Capacity Planning | 22109.7718
| 4 | 3 | Material handling | 11000 | 2 | 3 |  | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 10469.2011 | 3 | Material handling | 10469.2011
| 5 | 4 | Facilities planning | 17000 | 1 | 2 |  | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 16503.268 | 4 | Facilities planning | 16503.268
| 6 | 5 | Purchasing | 107000 | 2 | 4 |  | 0 | 0 | 0.33333 | 0.33333 | 0.33333 | 0 | 0 | 100841.67 | 5 | Purchasing | 100841.67
| 7 | 6 | Development of training | 18000 | 3 | 4 |  | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 16795.5098 | 6 | Development of training | 16795.5098
| 8 | 7 | Actual training | 51000 | 4 | 5 |  | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 46654.194 | 7 | Actual training | 46654.194
| 9 | 8 | Installation and Integration | 32000 | 4 | 6 |  | 0 | 0 | 0 | 0 | 0.33333 | 0.33333 | 0.33333 | 28987.1746 | 8 | Installation and Integration | 28987.1746
| 10 | 9 | Management of Project | 35000 | 1 | 6 |  | 0 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 32675.0135 | 9 | Management of Project | 32675.0135
| 11 | 10 | Finish | 0 | 6 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 10 | Finish | 0
[7 empty] | Cash Flow | 0 | 29000 | 70166.6667 | 63666.6667 | 86666.6667 | 42000 | 16500

## A_Line1_D
Capital Budget: A_Line1_D
=RV_SIMV(E15:H15)
Estimate | Sim
Percentile | 60% | [5 empty] | =RV_MEAN(E15:H15)
=RV_VAR(E15:H15)
|  | Work Breakdown Structure |  | Activity Costs | [7 empty] | Summary | [5 empty] | Estimate
|  | Level 1:A_Line1_D |  | Distributions |  | Most |  | Moments |  |  | WP | Level 2 | [5 empty] | Level 1:A_Line1_D
|  | L2 | Description | Dist. | Min. | Likely | Max. | Mean | Var. | S.D. | Cost | Index | Description | Mean | Var. | S.D. | Cost | Mean | Var. | S.D. | Cost
| 1 | 0 | Assembly Line | Tri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Assembly Line | 0 | 0 | 0 | 0 | 328533.334 | 276235554.3795 | 16620.3356 | 327971.5242 | Replication | 1 | SimX14 | P(SimX14)
| 2 | 1 | Process design | Tri | 11200 | 14000 | 19600 | 14933.333 | 3048888.8759 | 1746.1068 | 14100.3973 | 1 | Process design | 14933.333 | 3048888.8759 | 1746.1068 | 14100.3973 |  |  |  |  | Simulated Cell | $X$14 | 280000 | 0
| 3 | 2 | Capacity Planning | Tri | 18400 | 23000 | 32200 | 24533.334 | 8228888.8539 | 2868.604 | 21485.5792 | 2 | Capacity Planning | 24533.334 | 8228888.8539 | 2868.604 | 21485.5792 |  |  |  |  | Sample Size | 500 | 282200 | 0
| 4 | 3 | Material handling | Tri | 8800 | 11000 | 15400 | 11733.333 | 1882222.2142 | 1371.941 | 12470.0946 | 3 | Material handling | 11733.333 | 1882222.2142 | 1371.941 | 12470.0946 |  |  |  |  | Mean | 328377.1374 | 286600 | 0.004
| 5 | 4 | Facilities planning | Tri | 13600 | 17000 | 23800 | 18133.334 | 4495555.5364 | 2120.2725 | 21577.5234 | 4 | Facilities planning | 18133.334 | 4495555.5364 | 2120.2725 | 21577.5234 |  |  |  |  | Stand. Dev. | 15997.3647 | 291000 | 0.008
| 6 | 5 | Purchasing | Tri | 85600 | 107000 | 149800 | 114133.3359 | 178095554.7973 | 13345.2447 | 113871.4164 | 5 | Purchasing | 114133.3359 | 178095554.7973 | 13345.2447 | 113871.4164 |  |  |  |  | Minimum | 287492.3363 | 295400 | 0.008
| 7 | 6 | Development of training | Tri | 14400 | 18000 | 25200 | 19200 | 5039999.9785 | 2244.9944 | 16266.8844 | 6 | Development of training | 19200 | 5039999.9785 | 2244.9944 | 16266.8844 |  |  |  |  | Maximum | 387480.5669 | 299800 | 0.01
| 8 | 7 | Actual training | Tri | 40800 | 51000 | 71400 | 54400 | 40459999.8277 | 6360.8175 | 59102.2333 | 7 | Actual training | 54400 | 40459999.8277 | 6360.8175 | 59102.2333 |  |  |  |  | Mode | #N/A | 304200 | 0.02
| 9 | 8 | Installation and Integration | Tri | 25600 | 32000 | 44800 | 34133.332 | 15928888.8211 | 3991.1012 | 32675.5087 | 8 | Installation and Integration | 34133.332 | 15928888.8211 | 3991.1012 | 32675.5087 |  |  |  |  | Mid Range | Frequency | 308600 | 0.068
| 10 | 9 | Management of Project | Tri | 28000 | 35000 | 49000 | 37333.332 | 19055555.4744 | 4365.2669 | 36421.887 | 9 | Management of Project | 37333.332 | 19055555.4744 | 4365.2669 | 36421.887 |  |  |  |  | 280000 | 0 | 313000 | 0.1
| 11 | 10 | Finish | Tri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Finish | 0 | 0 | 0 | 0 |  |  |  |  | 282200 | 0 | 317400 | 0.082
[22 empty] | 286600 | 0.004 | 321800 | 0.126
[22 empty] | 291000 | 0.008 | 326200 | 0.116
[9 empty] | =A_Line1_D_UnitMean | [12 empty] | 295400 | 0.008 | 330600 | 0.1
[22 empty] | 299800 | 0.01 | 335000 | 0.09
[9 empty] | =RV_Inverse(E15:H15,A_Line1_D_Percentile) | [12 empty] | 304200 | 0.02 | 339400 | 0.058
[22 empty] | 308600 | 0.068 | 343800 | 0.062
[22 empty] | 313000 | 0.1 | 348200 | 0.05
[22 empty] | 317400 | 0.082 | 352600 | 0.038
[22 empty] | 321800 | 0.126 | 357000 | 0.02
[22 empty] | 326200 | 0.116 | 361400 | 0.02
[22 empty] | 330600 | 0.1 | 365800 | 0.004
[22 empty] | 335000 | 0.09 | 370200 | 0.01
[22 empty] | 339400 | 0.058 | 374600 | 0.004
[22 empty] | 343800 | 0.062 | 379000 | 0
[22 empty] | 348200 | 0.05 | 383400 | 0
[22 empty] | 352600 | 0.038 | 387800 | 0.002
[22 empty] | 357000 | 0.02 | 390000 | 0
[22 empty] | 361400 | 0.02
[22 empty] | 365800 | 0.004
[22 empty] | 370200 | 0.01
[22 empty] | 374600 | 0.004
[22 empty] | 379000 | 0
[22 empty] | 383400 | 0
[22 empty] | 387800 | 0.002
[22 empty] | 390000 | 0

## A_Line_Op
Life Cycle Cost: A_Line_Op
|  | Cost Breakdown Structure | [13 empty] | Summary |  |  | Estimate
|  | Level 1:A_Line_Op |  |  |  | Units |  |  |  | Units/ | Fixed | Unit | Item |  | Volume | Level 2 |  | Prod. | Level 1:A_Line_Op
|  | L2 | L3 | L4 | Description | N1 | N2 | N3 | N4 | Item | Cost | Cost | Cost | Mix | 30000 | Index | Description | Cost | Cost
| 1 | 0 | 0 | 0 | Line Operations | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Line Operations | 0 | -176390.4059
| 2 | 1 | 0 | 0 | Product A | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.1 | 0 | 1 | Product A | 140066.3379
| 3 | 1 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.1 | 0 | 2 | Revenue from A Sales | -186000
| 4 | 1 | 1 | 1 | Boards1 | 1 | 1 | 1 | 0.62988 | 0.62988 | 0 | 20 | 12.5976 | 0.1 | 37792.8962 | 3 | Product B | 500146.8013
| 5 | 1 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0.59673 | 0.59673 | 0 | 30 | 17.9019 | 0.1 | 53705.6939 | 4 | Revenue from B Sales | -720000
| 6 | 1 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 5.102 | 0.1 | 15306.1222 | 5 | Product C | 606396.4549
| 7 | 1 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99568 | 0.99568 | 0 | 1 | 0.99568 | 0.1 | 2987.0312 | 6 | Revenue from C Sales | -825000
| 8 | 1 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.1 | 0 | 7 | Fixed Costs | 308000
| 9 | 1 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0.45918 | 0.1 | 1377.551 | 8 | Overhead | 0
| 10 | 1 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0.96372 | 0.1 | 2891.1565
| 11 | 1 | 1 | 3 | SMT | 1 | 1 | 1 | 0.025195 | 0.025195 | 0 | 20 | 0.50391 | 0.1 | 1511.7158
| 12 | 1 | 1 | 4 | TH | 1 | 1 | 1 | 0.06564 | 0.06564 | 0 | 10 | 0.6564 | 0.1 | 1969.2088
| 13 | 1 | 1 | 5 | Labor | 1 | 1 | 1 | 0.37542 | 0.37542 | 0 | 20 | 7.5083 | 0.1 | 22524.9624
| 14 | 2 | 0 | 0 | Revenue from A Sales | 1 | 1 | 1 | 1 | 1 | 0 | -62 | -62 | 0.1 | -186000
| 15 | 3 | 0 | 0 | Product B | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.4 | 0
| 16 | 3 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.4 | 0
| 17 | 3 | 1 | 1 | Boards1 | 1 | 1 | 1 | 1.1338 | 1.1338 | 0 | 20 | 22.6757 | 0.4 | 272108.8527
| 18 | 3 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0.11935 | 0.11935 | 0 | 30 | 3.5804 | 0.4 | 42964.5551
| 19 | 3 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 5.102 | 0.4 | 61224.4886
| 20 | 3 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99833 | 0.99833 | 0 | 1 | 0.99833 | 0.4 | 11979.95
| 21 | 3 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.4 | 0
| 22 | 3 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0.45918 | 0.4 | 5510.204
| 23 | 3 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0.96372 | 0.4 | 11564.6259
| 24 | 3 | 1 | 3 | SMT | 1 | 1 | 1 | 0.045351 | 0.045351 | 0 | 20 | 0.90703 | 0.4 | 10884.3541
| 25 | 3 | 1 | 4 | TH | 1 | 1 | 1 | 0.013128 | 0.013128 | 0 | 10 | 0.13128 | 0.4 | 1575.367
| 26 | 3 | 1 | 5 | Labor | 1 | 1 | 1 | 0.34306 | 0.34306 | 0 | 20 | 6.8612 | 0.4 | 82334.404
| 27 | 4 | 0 | 0 | Revenue from B Sales | 1 | 1 | 1 | 1 | 1 | 0 | -60 | -60 | 0.4 | -720000
| 28 | 5 | 0 | 0 | Product C | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.5 | 0
| 29 | 5 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.5 | 0
| 30 | 5 | 1 | 1 | Boards1 | 1 | 1 | 1 | 1.2598 | 1.2598 | 0 | 20 | 25.1953 | 0.5 | 377928.962
| 31 | 5 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0 | 0 | 0 | 30 | 0 | 0.5 | 0
| 32 | 5 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 5.102 | 0.5 | 76530.6108
| 33 | 5 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99899 | 0.99899 | 0 | 1 | 0.99899 | 0.5 | 14984.8831
| 34 | 5 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.5 | 0
| 35 | 5 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0.45918 | 0.5 | 6887.755
| 36 | 5 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0.96372 | 0.5 | 14455.7824
| 37 | 5 | 1 | 3 | SMT | 1 | 1 | 1 | 0.050391 | 0.050391 | 0 | 20 | 1.0078 | 0.5 | 15117.1585
| 38 | 5 | 1 | 4 | TH | 1 | 1 | 1 | 0 | 0 | 0 | 10 | 0 | 0.5 | 0
| 39 | 5 | 1 | 5 | Labor | 1 | 1 | 1 | 0.33497 | 0.33497 | 0 | 20 | 6.6994 | 0.5 | 100491.3032
| 40 | 6 | 0 | 0 | Revenue from C Sales | 1 | 1 | 1 | 1 | 1 | 0 | -55 | -55 | 0.5 | -825000
| 41 | 7 | 0 | 0 | Fixed Costs | 1 | 1 | 1 | 1 | 1 | 308000 | 0 | 0 | 1 | 308000
| 42 | 8 | 0 | 0 | Overhead | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0
-15.3112
-18.3211
-14.5736

## A_Line_Op1
Life Cycle Cost: A_Line_Op1
|  | Cost Breakdown Structure |  |  |  | Quantity | 1 | [8 empty] | Total Cost | Summary |  |  | Estimate
|  | Level 1:A_Line_Op1 |  |  |  | Units |  |  |  |  | Fixed | Var. | Sub | Item |  | Volume | Level 2 |  | Prod. | Level 1:A_Line_Op1
|  | L2 | L3 | L4 | Description | N1 | N2 | N3 | N4 | Units | Cost | Cost | Total | Cost | Mix | 30000 | Index | Description | Cost | Cost
| 1 | 0 | 0 | 0 | Line Operations | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Line Operations | 0 | -26390.4059
| 2 | 1 | 0 | 0 | Product A | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.1 | 0 | 1 | Product A | 140066.3379
| 3 | 1 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.1 | 0 | 2 | Revenue from A Sales | -186000
| 4 | 1 | 1 | 1 | Boards1 | 1 | 1 | 1 | 0.62988 | 0.62988 | 0 | 20 | 0 | 12.5976 | 0.1 | 37792.8962 | 3 | Product B | 500146.8013
| 5 | 1 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0.59673 | 0.59673 | 0 | 30 | 0 | 17.9019 | 0.1 | 53705.6939 | 4 | Revenue from B Sales | -720000
| 6 | 1 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 0 | 5.102 | 0.1 | 15306.1222 | 5 | Product C | 606396.4549
| 7 | 1 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99568 | 0.99568 | 0 | 1 | 0 | 0.99568 | 0.1 | 2987.0312 | 6 | Revenue from C Sales | -825000
| 8 | 1 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.1 | 0 | 7 | Fixed Costs | 308000
| 9 | 1 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0 | 0.45918 | 0.1 | 1377.551 | 8 | Overhead | 150000
| 10 | 1 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0 | 0.96372 | 0.1 | 2891.1565
| 11 | 1 | 1 | 3 | SMT | 1 | 1 | 1 | 0.025195 | 0.025195 | 0 | 20 | 0 | 0.50391 | 0.1 | 1511.7158
| 12 | 1 | 1 | 4 | TH | 1 | 1 | 1 | 0.06564 | 0.06564 | 0 | 10 | 0 | 0.6564 | 0.1 | 1969.2088 | Subtotal Formulas
| 13 | 1 | 1 | 5 | Labor | 1 | 1 | 1 | 0.37542 | 0.37542 | 0 | 20 | 2 | 7.5083 | 0.1 | 22524.9624 | =M26*P26
| 14 | 2 | 0 | 0 | Revenue from A Sales | 1 | 1 | 1 | 1 | 1 | 0 | -62 | 0 | -62 | 0.1 | -186000
| 15 | 3 | 0 | 0 | Product B | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.4 | 0
| 16 | 3 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.4 | 0
| 17 | 3 | 1 | 1 | Boards1 | 1 | 1 | 1 | 1.1338 | 1.1338 | 0 | 20 | 0 | 22.6757 | 0.4 | 272108.8527
| 18 | 3 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0.11935 | 0.11935 | 0 | 30 | 0 | 3.5804 | 0.4 | 42964.5551
| 19 | 3 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 0 | 5.102 | 0.4 | 61224.4886
| 20 | 3 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99833 | 0.99833 | 0 | 1 | 0 | 0.99833 | 0.4 | 11979.95
| 21 | 3 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.4 | 0
| 22 | 3 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0 | 0.45918 | 0.4 | 5510.204
| 23 | 3 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0 | 0.96372 | 0.4 | 11564.6259
| 24 | 3 | 1 | 3 | SMT | 1 | 1 | 1 | 0.045351 | 0.045351 | 0 | 20 | 0 | 0.90703 | 0.4 | 10884.3541
| 25 | 3 | 1 | 4 | TH | 1 | 1 | 1 | 0.013128 | 0.013128 | 0 | 10 | 0 | 0.13128 | 0.4 | 1575.367
| 26 | 3 | 1 | 5 | Labor | 1 | 1 | 1 | 0.34306 | 0.34306 | 0 | 20 | 8 | 6.8612 | 0.4 | 82334.404 | =M39*P39
| 27 | 4 | 0 | 0 | Revenue from B Sales | 1 | 1 | 1 | 1 | 1 | 0 | -60 | 0 | -60 | 0.4 | -720000
| 28 | 5 | 0 | 0 | Product C | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0
| 29 | 5 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0
| 30 | 5 | 1 | 1 | Boards1 | 1 | 1 | 1 | 1.2598 | 1.2598 | 0 | 20 | 0 | 25.1953 | 0.5 | 377928.962
| 31 | 5 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0 | 0 | 0 | 30 | 0 | 0 | 0.5 | 0
| 32 | 5 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 0 | 5.102 | 0.5 | 76530.6108
| 33 | 5 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99899 | 0.99899 | 0 | 1 | 0 | 0.99899 | 0.5 | 14984.8831
| 34 | 5 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0
| 35 | 5 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0 | 0.45918 | 0.5 | 6887.755
| 36 | 5 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0 | 0.96372 | 0.5 | 14455.7824
| 37 | 5 | 1 | 3 | SMT | 1 | 1 | 1 | 0.050391 | 0.050391 | 0 | 20 | 0 | 1.0078 | 0.5 | 15117.1585
| 38 | 5 | 1 | 4 | TH | 1 | 1 | 1 | 0 | 0 | 0 | 10 | 0 | 0 | 0.5 | 0
| 39 | 5 | 1 | 5 | Labor | 1 | 1 | 1 | 0.33497 | 0.33497 | 0 | 20 | 10 | 6.6994 | 0.5 | 100491.3032 | =M52*P52
| 40 | 6 | 0 | 0 | Revenue from C Sales | 1 | 1 | 1 | 1 | 1 | 0 | -55 | 0 | -55 | 0.5 | -825000
| 41 | 7 | 0 | 0 | Fixed Costs | 1 | 1 | 1 | 1 | 1 | 308000 | 0 | 0 | 0 | 1 | 308000
| 42 | 7 | 0 | 0 | Total Labor | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 0 | 1 | 0 | =N26+N39+N52
| 43 | 8 | 0 | 0 | Overhead | 1 | 1 | 1 | 1 | 1 | 0 | 5 | 0 | 5 | 1 | 150000
[5 empty] | Overhead Rate | 0.25 | [6 empty] | =N55*G58

## A_Line_Op_Time1
Life Cycle Cost: A_Line_Op_Time1
Cost/Time
[16 empty] | Rate | 0%
|  | Cost Breakdown Structure |  |  |  | Quantity | 1 | [7 empty] | Time | 0 | 1 | 2 | 3 | 4 | 5 | 6
|  | Level 1:A_Line_Op_Time1 |  |  |  | Units |  |  |  |  | Fixed | Var. | Sub | Item | P/F | [7 empty] | NPW | bar: Rate 0 to 0% 6
|  | L2 | L3 | L4 | Description | N1 | N2 | N3 | N4 | Units | Cost | Cost | Total | Cost | Prod. | 0 | 5000 | 7000 | 10000 | 5000 | 2000 | 1000 | Cost
| 1 | 0 | 0 | 0 | Line Operations | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| 2 | 1 | 0 | 0 | Product A | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| 3 | 1 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| 4 | 1 | 1 | 1 | Boards1 | 1 | 1 | 1 | 0.62988 | 0.62988 | 0 | 20 | 0 | 12.5976 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 37792.8962
| 5 | 1 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0.59673 | 0.59673 | 0 | 30 | 0 | 17.9019 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 53705.6939
| 6 | 1 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 0 | 5.102 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 15306.1222
| 7 | 1 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99568 | 0.99568 | 0 | 1 | 0 | 0.99568 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 2987.0312
| 8 | 1 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| 9 | 1 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0 | 0.45918 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1377.551
| 10 | 1 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0 | 0.96372 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 2891.1565
| 11 | 1 | 1 | 3 | SMT | 1 | 1 | 1 | 0.025195 | 0.025195 | 0 | 20 | 0 | 0.50391 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1511.7158
| 12 | 1 | 1 | 4 | TH | 1 | 1 | 1 | 0.06564 | 0.06564 | 0 | 10 | 0 | 0.6564 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1969.2088
| 13 | 1 | 1 | 5 | Labor | 1 | 1 | 1 | 0.37542 | 0.37542 | 0 | 20 | 2 | 7.5083 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 22524.9624
| 14 | 2 | 0 | 0 | Revenue from A Sales | 1 | 1 | 1 | 1 | 1 | 0 | -62 | 0 | -62 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | -186000
| 15 | 3 | 0 | 0 | Product B | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0
| 16 | 3 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0
| 17 | 3 | 1 | 1 | Boards1 | 1 | 1 | 1 | 1.1338 | 1.1338 | 0 | 20 | 0 | 22.6757 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 272108.8527
| 18 | 3 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0.11935 | 0.11935 | 0 | 30 | 0 | 3.5804 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 42964.5551
| 19 | 3 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 0 | 5.102 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 61224.4886
| 20 | 3 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99833 | 0.99833 | 0 | 1 | 0 | 0.99833 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 11979.95
| 21 | 3 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0
| 22 | 3 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0 | 0.45918 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 5510.204
| 23 | 3 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0 | 0.96372 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 11564.6259
| 24 | 3 | 1 | 3 | SMT | 1 | 1 | 1 | 0.045351 | 0.045351 | 0 | 20 | 0 | 0.90703 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 10884.3541
| 25 | 3 | 1 | 4 | TH | 1 | 1 | 1 | 0.013128 | 0.013128 | 0 | 10 | 0 | 0.13128 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1575.367
| 26 | 3 | 1 | 5 | Labor | 1 | 1 | 1 | 0.34306 | 0.34306 | 0 | 20 | 8 | 6.8612 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 82334.404
| 27 | 4 | 0 | 0 | Revenue from B Sales | 1 | 1 | 1 | 1 | 1 | 0 | -60 | 0 | -60 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | -720000
| 28 | 5 | 0 | 0 | Product C | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 29 | 5 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 30 | 5 | 1 | 1 | Boards1 | 1 | 1 | 1 | 1.2598 | 1.2598 | 0 | 20 | 0 | 25.1953 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 377928.962
| 31 | 5 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0 | 0 | 0 | 30 | 0 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 32 | 5 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 0 | 5.102 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 76530.6108
| 33 | 5 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99899 | 0.99899 | 0 | 1 | 0 | 0.99899 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 14984.8831
| 34 | 5 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 35 | 5 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0 | 0.45918 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6887.755
| 36 | 5 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0 | 0.96372 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 14455.7824
| 37 | 5 | 1 | 3 | SMT | 1 | 1 | 1 | 0.050391 | 0.050391 | 0 | 20 | 0 | 1.0078 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 15117.1585
| 38 | 5 | 1 | 4 | TH | 1 | 1 | 1 | 0 | 0 | 0 | 10 | 0 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 39 | 5 | 1 | 5 | Labor | 1 | 1 | 1 | 0.33497 | 0.33497 | 0 | 20 | 10 | 6.6994 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 100491.3032
| 40 | 6 | 0 | 0 | Revenue from C Sales | 1 | 1 | 1 | 1 | 1 | 0 | -55 | 0 | -55 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | -825000
| 41 | 7 | 0 | 0 | Fixed Costs | 1 | 1 | 1 | 1 | 1 | 308000 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 308000
| 42 | 7 | 0 | 0 | Total Labor | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| 43 | 8 | 0 | 0 | Overhead | 1 | 1 | 1 | 1 | 1 | 0 | 5 | 0 | 5 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 150000
[15 empty] | Cash Flow | 308000 | -55731.7343 | -78024.428 | -111463.4686 | -55731.7343 | -22292.6937 | -11146.3469
[5 empty] | Overhead Rate | 0.25 | [6 empty] | =N55*G58

## A_Line_Op_Time
Life Cycle Cost: A_Line_Op_Time
[15 empty] | Time/Cost |  |  |  |  | Total | 30000
[15 empty] | Rate | 0%
|  | Cost Breakdown Structure | [11 empty] | Time | 0 | 1 | 2 | 3 | 4 | 5 | 6 |  | Summary |  |  | Estimate
|  | Level 1:A_Line_Op_Time |  |  |  | Units |  |  |  | Units/ | Fixed | Unit | Item | P/F | [7 empty] | NPW | Level 2 |  | NPW | Level 1:A_Line_Op_Time | bar: Rate 0 to 0% 6
|  | L2 | L3 | L4 | Description | N1 | N2 | N3 | N4 | Item | Cost | Cost | Cost | Prod. | 0 | 5000 | 7000 | 10000 | 5000 | 2000 | 1000 | Cost | Index | Description | Cost | NPW Cost
| 1 | 0 | 0 | 0 | Line Operations | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Line Operations | 0 | -176390.4059
| 2 | 1 | 0 | 0 | Product A | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 1 | Product A | 140066.3379
| 3 | 1 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 2 | Revenue from A Sales | -186000
| 4 | 1 | 1 | 1 | Boards1 | 1 | 1 | 1 | 0.62988 | 0.62988 | 0 | 20 | 12.5976 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 37792.8962 | 3 | Product B | 500146.8013
| 5 | 1 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0.59673 | 0.59673 | 0 | 30 | 17.9019 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 53705.6939 | 4 | Revenue from B Sales | -720000
| 6 | 1 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 5.102 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 15306.1222 | 5 | Product C | 606396.4549
| 7 | 1 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99568 | 0.99568 | 0 | 1 | 0.99568 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 2987.0312 | 6 | Revenue from C Sales | -825000
| 8 | 1 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 7 | Fixed Costs | 308000
| 9 | 1 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0.45918 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1377.551 | 8 | Overhead | 0
| 10 | 1 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0.96372 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 2891.1565
| 11 | 1 | 1 | 3 | SMT | 1 | 1 | 1 | 0.025195 | 0.025195 | 0 | 20 | 0.50391 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1511.7158
| 12 | 1 | 1 | 4 | TH | 1 | 1 | 1 | 0.06564 | 0.06564 | 0 | 10 | 0.6564 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1969.2088
| 13 | 1 | 1 | 5 | Labor | 1 | 1 | 1 | 0.37542 | 0.37542 | 0 | 20 | 7.5083 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 22524.9624
| 14 | 2 | 0 | 0 | Revenue from A Sales | 1 | 1 | 1 | 1 | 1 | 0 | -62 | -62 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | -186000
| 15 | 3 | 0 | 0 | Product B | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0
| 16 | 3 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0
| 17 | 3 | 1 | 1 | Boards1 | 1 | 1 | 1 | 1.1338 | 1.1338 | 0 | 20 | 22.6757 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 272108.8527
| 18 | 3 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0.11935 | 0.11935 | 0 | 30 | 3.5804 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 42964.5551
| 19 | 3 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 5.102 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 61224.4886
| 20 | 3 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99833 | 0.99833 | 0 | 1 | 0.99833 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 11979.95
| 21 | 3 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0
| 22 | 3 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0.45918 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 5510.204
| 23 | 3 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0.96372 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 11564.6259
| 24 | 3 | 1 | 3 | SMT | 1 | 1 | 1 | 0.045351 | 0.045351 | 0 | 20 | 0.90703 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 10884.3541
| 25 | 3 | 1 | 4 | TH | 1 | 1 | 1 | 0.013128 | 0.013128 | 0 | 10 | 0.13128 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1575.367
| 26 | 3 | 1 | 5 | Labor | 1 | 1 | 1 | 0.34306 | 0.34306 | 0 | 20 | 6.8612 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 82334.404
| 27 | 4 | 0 | 0 | Revenue from B Sales | 1 | 1 | 1 | 1 | 1 | 0 | -60 | -60 |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | -720000
| 28 | 5 | 0 | 0 | Product C | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 29 | 5 | 1 | 0 | Material | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 30 | 5 | 1 | 1 | Boards1 | 1 | 1 | 1 | 1.2598 | 1.2598 | 0 | 20 | 25.1953 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 377928.962
| 31 | 5 | 1 | 2 | Boards2 | 1 | 1 | 1 | 0 | 0 | 0 | 30 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 32 | 5 | 1 | 2 | Packs | 1 | 1 | 1 | 1.0204 | 1.0204 | 0 | 5 | 5.102 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 76530.6108
| 33 | 5 | 1 | 3 | Supplies | 1 | 1 | 1 | 0.99899 | 0.99899 | 0 | 1 | 0.99899 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 14984.8831
| 34 | 5 | 2 | 0 | Resources | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 35 | 5 | 1 | 1 | Pack | 1 | 1 | 1 | 0.091837 | 0.091837 | 0 | 5 | 0.45918 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6887.755
| 36 | 5 | 1 | 2 | RunIn | 1 | 1 | 1 | 0.19274 | 0.19274 | 0 | 5 | 0.96372 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 14455.7824
| 37 | 5 | 1 | 3 | SMT | 1 | 1 | 1 | 0.050391 | 0.050391 | 0 | 20 | 1.0078 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 15117.1585
| 38 | 5 | 1 | 4 | TH | 1 | 1 | 1 | 0 | 0 | 0 | 10 | 0 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| 39 | 5 | 1 | 5 | Labor | 1 | 1 | 1 | 0.33497 | 0.33497 | 0 | 20 | 6.6994 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 100491.3032
| 40 | 6 | 0 | 0 | Revenue from C Sales | 1 | 1 | 1 | 1 | 1 | 0 | -55 | -55 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | -825000
| 41 | 7 | 0 | 0 | Fixed Costs | 1 | 1 | 1 | 1 | 1 | 308000 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 308000
| 42 | 8 | 0 | 0 | Overhead | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[14 empty] | Cash Flow | 308000 | -80731.7343 | -113024.428 | -161463.4686 | -80731.7343 | -32292.6937 | -16146.3469
[20 empty] | IRR = | 18.24%

## Sheet1
Units/Item
Product | A | B | C |  | Cost/Unit
Material |  |  |  | Material
Boards1 | 0.62988 | 1.1338 | 1.2598 | Boards1 | 20
Boards2 | 0.59673 | 0.11935 | 0 | Boards2 | 30 | Year | 1 | 2 | 3 | 4 | 5 | 6 | Total
Packs | 1.0204 | 1.0204 | 1.0204 | Packs | 5 | Sales | 5000 | 7000 | 10000 | 5000 | 2000 | 1000 | 30000
Supplies | 0.99568 | 0.99833 | 0.99899 | Supplies | 1
Resources |  |  |  | Resources
Pack | 0.091837 | 0.091837 | 0.091837 | Pack | 5
RunIn | 0.19274 | 0.19274 | 0.19274 | RunIn | 5
SMT | 0.025195 | 0.045351 | 0.050391 | SMT | 20
TH | 0.06564 | 0.013128 | 0 | TH | 10
Labor | 0.37542 | 0.34306 | 0.33497 | Labor | 20
Product | A | B | C
Unit Revenue | 62 | 60 | 55
Mix (%) | 10 | 40 | 50