## Data
Work Breakdown Structure |  | Normal Assumption
| Description | Mean | Std. dev.
1 | Process design | 14 | 5
2 | Capacity Planning | 23 | 2
3 | Material handling | 11 | 2
4 | Facilities planning | 17 | 2
5 | Purchasing | 107 | 10
6 | Development of training | 18 | 5
7 | Actual training | 51 | 4
8 | Installation and Integration | 32 | 10
9 | Management of Project | 35 | 3

## P1
Work Breakdown Structure |  | Normal Assumption
| Description | Mean | Std. dev. | Variance | 60th perc.
1 | Process design | 14 | 5 | 25 | 15.2667
2 | Capacity Planning | 23 | 2 | 4 | 23.5067
3 | Material handling | 11 | 2 | 4 | 11.5067
4 | Facilities planning | 17 | 2 | 4 | 17.5067
5 | Purchasing | 107 | 10 | 100 | 109.5335
6 | Development of training | 18 | 5 | 25 | 19.2667
7 | Actual training | 51 | 4 | 16 | 52.0134
8 | Installation and Integration | 32 | 10 | 100 | 34.5335
9 | Management of Project | 35 | 3 | 9 | 35.76
| Sum | 308 |  | 287 | 318.8939
|  | Mean | Std. dev. | 60th per. Est.
| Project Cost | 308 | 16.9411 | 318.8939
| P(C>60th perc.) | 0.2601
| P(C < 300) | 0.31838
| 60th percentile of project cost | 312.292
90% interval estimate
| Alpha | 0.1
| Lower | 280.1344
| Upper | 335.8656

## P2
Work Breakdown Structure |  | Normal Assumption |  |  |  | Random Variable | Purchase |  | f(Purchase)
[6 empty] | Distribution | Beta | 80 | #VALUE! |  | f(Install) |  | f(Manage)
| Description | Mean | Std. dev. | Variance | 60th perc. | alpha | 2 | 81.25 | #VALUE! | 30 | #VALUE! | 30 | 0.1
1 | Process design | 14 | 5 | 25 | 15.2667 | beta | 8 | 82.5 | #VALUE! | 31.25 | #VALUE! | 30.5 | #VALUE!
2 | Capacity Planning | 23 | 2 | 4 | 23.5067 | lower (a) | 80 | 83.75 | #VALUE! | 32.5 | #VALUE! | 31 | #VALUE!
3 | Material handling | 11 | 2 | 4 | 11.5067 | upper (b) | 130 | 85 | #VALUE! | 33.75 | #VALUE! | 31.5 | #VALUE!
4 | Facilities planning | 17 | 2 | 4 | 17.5067 | Mean | #VALUE! | 86.25 | #VALUE! | 35 | #VALUE! | 32 | #VALUE!
5 | Purchasing | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Var. | #VALUE! | 87.5 | #VALUE! | 36.25 | #VALUE! | 32.5 | #VALUE!
6 | Development of training | 18 | 5 | 25 | 19.2667 | e | 0.6 | 88.75 | #VALUE! | 37.5 | #VALUE! | 33 | #VALUE!
7 | Actual training | 51 | 4 | 16 | 52.0134 | Inverse P(e) | #VALUE! | 90 | #VALUE! | 38.75 | #VALUE! | 33.5 | #VALUE!
8 | Installation and Integration | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | 91.25 | #VALUE! | 40 | #VALUE! | 34 | #VALUE!
9 | Management of Project | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Random Variable | Install | 92.5 | #VALUE! | 41.25 | #VALUE! | 34.5 | #VALUE!
| Sum | #VALUE! |  | #VALUE! | #VALUE! | Distribution | Triangular | 93.75 | #VALUE! | 42.5 | #VALUE! | 35 | #VALUE!
[6 empty] | lower limit (a) | 30 | 95 | #VALUE! | 43.75 | #VALUE! | 35.5 | #VALUE!
|  | Mean | Std. dev. | 60th per. Est. |  | mode (m) | 70 | 96.25 | #VALUE! | 45 | #VALUE! | 36 | #VALUE!
| Project Cost | #VALUE! | #VALUE! | #VALUE! |  | upper limit (b) | 80 | 97.5 | #VALUE! | 46.25 | #VALUE! | 36.5 | #VALUE!
[6 empty] | Mean | #VALUE! | 98.75 | #VALUE! | 47.5 | #VALUE! | 37 | #VALUE!
| P(C>60th perc.) | #VALUE! |  |  |  | Var. | #VALUE! | 100 | #VALUE! | 48.75 | #VALUE! | 37.5 | #VALUE!
[6 empty] | e | 0.6 | 101.25 | #VALUE! | 50 | #VALUE! | 38 | #VALUE!
| P(C < 300) | #VALUE! |  |  |  | Inverse P(e) | #VALUE! | 102.5 | #VALUE! | 51.25 | #VALUE! | 38.5 | #VALUE!
[8 empty] | 103.75 | #VALUE! | 52.5 | #VALUE! | 39 | #VALUE!
| 60th percentile of project cost | #VALUE! |  |  |  | Random Variable | Manage | 105 | #VALUE! | 53.75 | #VALUE! | 39.5 | #VALUE!
[6 empty] | Distribution | Uniform | 106.25 | #VALUE! | 55 | #VALUE! | 40 | #VALUE!
| 90% interval estimate |  |  |  |  | lower limit (a) | 30 | 107.5 | #VALUE! | 56.25 | #VALUE!
| Alpha | 0.1 |  |  |  | upper limit (b) | 40 | 108.75 | #VALUE! | 57.5 | #VALUE!
| Lower | #VALUE! |  |  |  | Mean | #VALUE! | 110 | #VALUE! | 58.75 | #VALUE!
| Upper | #VALUE! |  |  |  | Var. | #VALUE! | 111.25 | #VALUE! | 60 | #VALUE!
[6 empty] | e | 0.6 | 112.5 | #VALUE! | 61.25 | #VALUE!
[6 empty] | Inverse P(e) | #VALUE! | 113.75 | #VALUE! | 62.5 | #VALUE!
[8 empty] | 115 | #VALUE! | 63.75 | #VALUE!
[8 empty] | 116.25 | #VALUE! | 65 | #VALUE!
[8 empty] | 117.5 | #VALUE! | 66.25 | #VALUE!
[8 empty] | 118.75 | #VALUE! | 67.5 | #VALUE!
[8 empty] | 120 | #VALUE! | 68.75 | #VALUE!
[8 empty] | 121.25 | #VALUE! | 70 | #VALUE!
[8 empty] | 122.5 | #VALUE! | 71.25 | #VALUE!
[8 empty] | 123.75 | #VALUE! | 72.5 | #VALUE!
[8 empty] | 125 | #VALUE! | 73.75 | #VALUE!
[8 empty] | 126.25 | #VALUE! | 75 | #VALUE!
[8 empty] | 127.5 | #VALUE! | 76.25 | #VALUE!
[8 empty] | 128.75 | #VALUE! | 77.5 | #VALUE!
[8 empty] | 130 | #VALUE! | 78.75 | #VALUE!
[10 empty] | 80 | #VALUE!

## Est_1
Capital Budget: Est_1
Estimate | Sim
Percentile | 60%
|  | Work Breakdown Structure |  | Activity Costs | [8 empty] | Summary | [5 empty] | Estimate
|  | Level 1:Est_1 |  | Distributions |  |  |  |  | Moments |  |  | WP | Level 2 | [5 empty] | Level 1:Est_1
|  | L2 | Description | Dist. | Par1 | Par2 | Par3 | Par4 | Mean | Var. | S.D. | Cost | Index | Description | Mean | Var. | S.D. | Cost | Mean | Var. | S.D. | Cost
| 1 | 0 | Start | General | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | Start | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Replication | 1 | SimY14 | P(SimY14)
| 2 | 1 | Process design | Normal | 14 | 5 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1 | Process design | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Simulated Cell | $Y$14 | 260 | 0
| 3 | 2 | Capacity Planning | Normal | 23 | 2 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2 | Capacity Planning | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Sample Size | 1000 | 261.1 | 0
| 4 | 3 | Material handling | Normal | 11 | 2 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3 | Material handling | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Mean | 318.1922 | 263.3 | 0
| 5 | 4 | Facilities planning | Normal | 17 | 2 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 4 | Facilities planning | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Stand. Dev. | 15.629 | 265.5 | 0.001
| 6 | 5 | Purchasing | Beta | 2 | 8 | 80 | 130 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | Purchasing | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Skewness | -0.088961 | 267.7 | 0
| 7 | 6 | Development of training | Normal | 18 | 5 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 6 | Development of training | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Kurtosis | 0.0984 | 269.9 | 0.001
| 8 | 7 | Actual training | Normal | 51 | 4 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 7 | Actual training | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Minimum | 265.2069 | 272.1 | 0.001
| 9 | 8 | Installation and Integration | Tri | 30 | 70 | 80 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 8 | Installation and Integration | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Maximum | 366.3437 | 274.3 | 0.001
| 10 | 9 | Management of Project | uni | 30 | 40 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 9 | Management of Project | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Median | 318.682 | 276.5 | 0.003
| 11 | 10 | Finish | General | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 10 | Finish | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Mode | #N/A | 278.7 | 0.001
[23 empty] | Mid Range | Frequency | 280.9 | 0.002
[23 empty] | 260 | 0 | 283.1 | 0.009
[23 empty] | 261.1 | 0 | 285.3 | 0.008
[23 empty] | 263.3 | 0 | 287.5 | 0.007
[23 empty] | 265.5 | 0.001 | 289.7 | 0.016
[23 empty] | 267.7 | 0 | 291.9 | 0.007
[23 empty] | 269.9 | 0.001 | 294.1 | 0.013
[23 empty] | 272.1 | 0.001 | 296.3 | 0.019
[23 empty] | 274.3 | 0.001 | 298.5 | 0.031
[23 empty] | 276.5 | 0.003 | 300.7 | 0.03
[23 empty] | 278.7 | 0.001 | 302.9 | 0.038
[23 empty] | 280.9 | 0.002 | 305.1 | 0.031
[23 empty] | 283.1 | 0.009 | 307.3 | 0.041
[23 empty] | 285.3 | 0.008 | 309.5 | 0.041
[23 empty] | 287.5 | 0.007 | 311.7 | 0.037
[23 empty] | 289.7 | 0.016 | 313.9 | 0.062
[23 empty] | 291.9 | 0.007 | 316.1 | 0.059
[23 empty] | 294.1 | 0.013 | 318.3 | 0.068
[23 empty] | 296.3 | 0.019 | 320.5 | 0.06
[23 empty] | 298.5 | 0.031 | 322.7 | 0.056
[23 empty] | 300.7 | 0.03 | 324.9 | 0.052
[23 empty] | 302.9 | 0.038 | 327.1 | 0.05
[23 empty] | 305.1 | 0.031 | 329.3 | 0.035
[23 empty] | 307.3 | 0.041 | 331.5 | 0.037
[23 empty] | 309.5 | 0.041 | 333.7 | 0.042
[23 empty] | 311.7 | 0.037 | 335.9 | 0.033
[23 empty] | 313.9 | 0.062 | 338.1 | 0.024
[23 empty] | 316.1 | 0.059 | 340.3 | 0.021
[23 empty] | 318.3 | 0.068 | 342.5 | 0.019
[23 empty] | 320.5 | 0.06 | 344.7 | 0.011
[23 empty] | 322.7 | 0.056 | 346.9 | 0.006
[23 empty] | 324.9 | 0.052 | 349.1 | 0.006
[23 empty] | 327.1 | 0.05 | 351.3 | 0.004
[23 empty] | 329.3 | 0.035 | 353.5 | 0.007
[23 empty] | 331.5 | 0.037 | 355.7 | 0.003
[23 empty] | 333.7 | 0.042 | 357.9 | 0.002
[23 empty] | 335.9 | 0.033 | 360.1 | 0.002
[23 empty] | 338.1 | 0.024 | 362.3 | 0.001
[23 empty] | 340.3 | 0.021 | 364.5 | 0.001
[23 empty] | 342.5 | 0.019 | 366.7 | 0.001
[23 empty] | 344.7 | 0.011 | 368.9 | 0
[23 empty] | 346.9 | 0.006 | 370 | 0
[23 empty] | 349.1 | 0.006
[23 empty] | 351.3 | 0.004
[23 empty] | 353.5 | 0.007
[23 empty] | 355.7 | 0.003
[23 empty] | 357.9 | 0.002
[23 empty] | 360.1 | 0.002
[23 empty] | 362.3 | 0.001
[23 empty] | 364.5 | 0.001
[23 empty] | 366.7 | 0.001
[23 empty] | 368.9 | 0
[23 empty] | 370 | 0
[23 empty] | Mid Range | Cum. Freq.
[23 empty] | 260 | 0
[23 empty] | 261.1 | 0
[23 empty] | 263.3 | 0
[23 empty] | 265.5 | 0.001
[23 empty] | 267.7 | 0.001
[23 empty] | 269.9 | 0.002
[23 empty] | 272.1 | 0.003
[23 empty] | 274.3 | 0.004
[23 empty] | 276.5 | 0.007
[23 empty] | 278.7 | 0.008
[23 empty] | 280.9 | 0.01
[23 empty] | 283.1 | 0.019
[23 empty] | 285.3 | 0.027
[23 empty] | 287.5 | 0.034
[23 empty] | 289.7 | 0.05
[23 empty] | 291.9 | 0.057
[23 empty] | 294.1 | 0.07
[23 empty] | 296.3 | 0.089
[23 empty] | 298.5 | 0.12
[23 empty] | 300.7 | 0.15
[23 empty] | 302.9 | 0.188
[23 empty] | 305.1 | 0.219
[23 empty] | 307.3 | 0.26
[23 empty] | 309.5 | 0.301
[23 empty] | 311.7 | 0.338
[23 empty] | 313.9 | 0.4
[23 empty] | 316.1 | 0.459
[23 empty] | 318.3 | 0.527
[23 empty] | 320.5 | 0.587
[23 empty] | 322.7 | 0.643
[23 empty] | 324.9 | 0.695
[23 empty] | 327.1 | 0.745
[23 empty] | 329.3 | 0.78
[23 empty] | 331.5 | 0.817
[23 empty] | 333.7 | 0.859
[23 empty] | 335.9 | 0.892
[23 empty] | 338.1 | 0.916
[23 empty] | 340.3 | 0.937
[23 empty] | 342.5 | 0.956
[23 empty] | 344.7 | 0.967
[23 empty] | 346.9 | 0.973
[23 empty] | 349.1 | 0.979
[23 empty] | 351.3 | 0.983
[23 empty] | 353.5 | 0.99
[23 empty] | 355.7 | 0.993
[23 empty] | 357.9 | 0.995
[23 empty] | 360.1 | 0.997
[23 empty] | 362.3 | 0.998
[23 empty] | 364.5 | 0.999
[23 empty] | 366.7 | 1
[23 empty] | 368.9 | 1
[23 empty] | 370 | 1

## Assemble
Capital Budget: Assemble
Estimate | Sim
Percentile | 60%
|  | Work Breakdown Structure |  | Activity Costs | [8 empty] | Summary | [5 empty] | Estimate
|  | Level 1:Assemble |  | Distributions |  |  |  |  | Moments |  |  | WP | Level 2 | [5 empty] | Level 1:Assemble
|  | L2 | Description | Dist. | Par1 | Par2 | Par3 | Par4 | Mean | Var. | S.D. | Cost | Index | Description | Mean | Var. | S.D. | Cost | Mean | Var. | S.D. | Cost
| 1 | 0 | Start | General | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | Start | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Replication | 1 | SimY14 | P(SimY14)
| 2 | 1 | Process design | Normal | 14 | 5 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1 | Process design | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Simulated Cell | $Y$14 | 250 | 0
| 3 | 2 | Capacity Planning | Normal | 23 | 2 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2 | Capacity Planning | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Sample Size | 1000 | 251.2 | 0
| 4 | 3 | Material handling | Normal | 11 | 2 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3 | Material handling | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Mean | 319.3538 | 253.6 | 0
| 5 | 4 | Facilities planning | Normal | 17 | 2 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 4 | Facilities planning | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Stand. Dev. | 15.8567 | 256 | 0
| 6 | 5 | Purchasing | Beta | 2 | 8 | 80 | 130 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 5 | Purchasing | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Skewness | -0.11601 | 258.4 | 0.001
| 7 | 6 | Development of training | Normal | 18 | 5 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 6 | Development of training | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Kurtosis | 0.034924 | 260.8 | 0
| 8 | 7 | Actual training | Normal | 51 | 4 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 7 | Actual training | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Minimum | 257.6841 | 263.2 | 0
| 9 | 8 | Installation and Integration | Tri | 30 | 70 | 80 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 8 | Installation and Integration | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Maximum | 368.8086 | 265.6 | 0
| 10 | 9 | Management of Project | uni | 30 | 40 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 9 | Management of Project | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Median | 319.6666 | 268 | 0
| 11 | 10 | Finish | General | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 10 | Finish | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | Mode | #N/A | 270.4 | 0
[23 empty] | Mid Range | Frequency | 272.8 | 0.001
[19 empty] | P(C < 300) | #VALUE! |  |  | 250 | 0 | 275.2 | 0.001
[20 empty] | 0.6 |  |  | 251.2 | 0 | 277.6 | 0.006
[19 empty] | 60th percentile of project cost | #VALUE! |  |  | 253.6 | 0 | 280 | 0.002
[23 empty] | 256 | 0 | 282.4 | 0
[19 empty] | 90% interval estimate |  |  |  | 258.4 | 0.001 | 284.8 | 0.006
[19 empty] | Alpha | 0.1 |  |  | 260.8 | 0 | 287.2 | 0.011
[19 empty] | Lower | #VALUE! |  |  | 263.2 | 0 | 289.6 | 0.007
[19 empty] | Upper | #VALUE! |  |  | 265.6 | 0 | 292 | 0.018
[23 empty] | 268 | 0 | 294.4 | 0.018
[23 empty] | 270.4 | 0 | 296.8 | 0.02
[23 empty] | 272.8 | 0.001 | 299.2 | 0.037
[23 empty] | 275.2 | 0.001 | 301.6 | 0.031
[23 empty] | 277.6 | 0.006 | 304 | 0.03
[23 empty] | 280 | 0.002 | 306.4 | 0.045
[23 empty] | 282.4 | 0 | 308.8 | 0.036
[23 empty] | 284.8 | 0.006 | 311.2 | 0.044
[23 empty] | 287.2 | 0.011 | 313.6 | 0.057
[23 empty] | 289.6 | 0.007 | 316 | 0.061
[23 empty] | 292 | 0.018 | 318.4 | 0.066
[23 empty] | 294.4 | 0.018 | 320.8 | 0.066
[23 empty] | 296.8 | 0.02 | 323.2 | 0.053
[23 empty] | 299.2 | 0.037 | 325.6 | 0.061
[23 empty] | 301.6 | 0.031 | 328 | 0.047
[23 empty] | 304 | 0.03 | 330.4 | 0.048
[23 empty] | 306.4 | 0.045 | 332.8 | 0.046
[23 empty] | 308.8 | 0.036 | 335.2 | 0.045
[23 empty] | 311.2 | 0.044 | 337.6 | 0.031
[23 empty] | 313.6 | 0.057 | 340 | 0.026
[23 empty] | 316 | 0.061 | 342.4 | 0.02
[23 empty] | 318.4 | 0.066 | 344.8 | 0.016
[23 empty] | 320.8 | 0.066 | 347.2 | 0.012
[23 empty] | 323.2 | 0.053 | 349.6 | 0.011
[23 empty] | 325.6 | 0.061 | 352 | 0.008
[23 empty] | 328 | 0.047 | 354.4 | 0.003
[23 empty] | 330.4 | 0.048 | 356.8 | 0.003
[23 empty] | 332.8 | 0.046 | 359.2 | 0.002
[23 empty] | 335.2 | 0.045 | 361.6 | 0.001
[23 empty] | 337.6 | 0.031 | 364 | 0.002
[23 empty] | 340 | 0.026 | 366.4 | 0
[23 empty] | 342.4 | 0.02 | 368.8 | 0.001
[23 empty] | 344.8 | 0.016 | 370 | 0
[23 empty] | 347.2 | 0.012
[23 empty] | 349.6 | 0.011
[23 empty] | 352 | 0.008
[23 empty] | 354.4 | 0.003
[23 empty] | 356.8 | 0.003
[23 empty] | 359.2 | 0.002
[23 empty] | 361.6 | 0.001
[23 empty] | 364 | 0.002
[23 empty] | 366.4 | 0
[23 empty] | 368.8 | 0.001
[23 empty] | 370 | 0
[23 empty] | Mid Range | Cum. Freq.
[23 empty] | 250 | 0
[23 empty] | 251.2 | 0
[23 empty] | 253.6 | 0
[23 empty] | 256 | 0
[23 empty] | 258.4 | 0.001
[23 empty] | 260.8 | 0.001
[23 empty] | 263.2 | 0.001
[23 empty] | 265.6 | 0.001
[23 empty] | 268 | 0.001
[23 empty] | 270.4 | 0.001
[23 empty] | 272.8 | 0.002
[23 empty] | 275.2 | 0.003
[23 empty] | 277.6 | 0.009
[23 empty] | 280 | 0.011
[23 empty] | 282.4 | 0.011
[23 empty] | 284.8 | 0.017
[23 empty] | 287.2 | 0.028
[23 empty] | 289.6 | 0.035
[23 empty] | 292 | 0.053
[23 empty] | 294.4 | 0.071
[23 empty] | 296.8 | 0.091
[23 empty] | 299.2 | 0.128
[23 empty] | 301.6 | 0.159
[23 empty] | 304 | 0.189
[23 empty] | 306.4 | 0.234
[23 empty] | 308.8 | 0.27
[23 empty] | 311.2 | 0.314
[23 empty] | 313.6 | 0.371
[23 empty] | 316 | 0.432
[23 empty] | 318.4 | 0.498
[23 empty] | 320.8 | 0.564
[23 empty] | 323.2 | 0.617
[23 empty] | 325.6 | 0.678
[23 empty] | 328 | 0.725
[23 empty] | 330.4 | 0.773
[23 empty] | 332.8 | 0.819
[23 empty] | 335.2 | 0.864
[23 empty] | 337.6 | 0.895
[23 empty] | 340 | 0.921
[23 empty] | 342.4 | 0.941
[23 empty] | 344.8 | 0.957
[23 empty] | 347.2 | 0.969
[23 empty] | 349.6 | 0.98
[23 empty] | 352 | 0.988
[23 empty] | 354.4 | 0.991
[23 empty] | 356.8 | 0.994
[23 empty] | 359.2 | 0.996
[23 empty] | 361.6 | 0.997
[23 empty] | 364 | 0.999
[23 empty] | 366.4 | 0.999
[23 empty] | 368.8 | 1
[23 empty] | 370 | 1