## Instructions
Projects Add-in Demonstration
http://www.me.utexas.edu/~jensen/ORMM/omie/computation/unit/project/index.html
The workbook illustrates the several model forms available with the Projects add-in.
| • | This workbook has been saved in the Frozen mode. Choose the Links command to create the buttons that control the add-in activities.
| • | Problems with uncertainty use functions from the Random Variables add-in. The Links function also replaces functions from the Random Variables add-in when they are required.
| • | If you are transferring the workbook to be opened on another computer, use the links command to remove the buttons and replace functions used by the Random Variables add-in.
| • | If you use functions in cells outside the forms created by the add-in, these functions are not affected by the Links command. Use the Links command under the Edit menu to correct these links.
Economics Add-in
Topic
Pump |  | This is the Pump example. Activity data is entered on the worksheet.
Network |  | This worksheet contains information used by the solution of the Pump problem. No interaction with this sheet is necessary.
Schedule |  | This is the schedule worksheet for the Pump problem.
PumpCal |  | This is the Pump Problem with a calendar.
Network |  | This worksheet contains information used by the solution of the PumpCal problem. No interaction with this sheet is necessary.
Calendar |  | This is the calendar for the PumpCal problem.
Pump_RV |  | The Pump example with random activity times.

## Pump
Project Pump | [15 empty] | Times(Proj. Days) | [11 empty] | Gantt Parmeters
[16 empty] | Due | 59 | [9 empty] | Bucket | 1
| Solve | [14 empty] | Critical | 57 | [9 empty] | Start | 0
[16 empty] | Var. | 12.5 | [9 empty] | Horizon | 59
| Change |  | Gantt | [12 empty] | SD. | 3.5355 | [9 empty] | Extra | 10
[16 empty] | On Time Prob. | 0.7142
| Critical |  | Graph | [12 empty] | Slack | 2
[16 empty] | Late | 0
| Update |  | Schedule | [12 empty] | Current | 0
|  | Activity Data | [6 empty] | Resources | Activity Time Estimates | [8 empty] | Schedule Limits |  |  |  |  | Schedule Decisions |  |  |  | Gantt Chart
[11 empty] | Most |  |  |  |  | Time | Activity |  | Early | Late | Early | Late |  | Sched. | Sched. | Perc. |  | Proj. Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69
|  | Critical | Name | Description | Predecessors |  |  | Color | Crew | Min. | Likely | Max. | Mean | S.D. | Var. | Days | Delay | Sort | Start | Start | Finish | Finish | Slack | Start | Finish | Finished |  | Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 1 | Start | Activity Start |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0% |  | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 1 | A | POUR SLAB |  |  |  |  | 4 | 9 | 11 | 19 | 12 | 1.6667 | 2.7778 | 12 | 0 | 2 | 0 | 2 | 12 | 14 | 2 | 0 | 12 | 0% |  | POUR SLAB | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | B | ORDER PUMP UNIT |  |  |  |  | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0 | 3 | 0 | 29.75 | 0.25 | 30 | 29.75 | 0 | 0.25 | 0% |  | ORDER PUMP UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | C | CUT PATH |  |  |  |  | 6 | 20 | 30 | 40 | 30 | 3.3333 | 11.1111 | 30 | 0 | 4 | 0 | 11.6667 | 30 | 41.6667 | 11.6667 | 0 | 30 | 0% |  | CUT PATH | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | 1 | D | CURE SLAB | A |  |  |  | 0 | 24 | 24 | 24 | 24 | 0 | 0 | 24 | 0 | 5 | 12 | 14 | 36 | 38 | 2 | 12 | 36 | 0% |  | CURE SLAB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 0 | E | DELIVER UNIT | B |  |  |  | 0 | 3 | 9 | 9 | 8 | 1 | 1 | 8 | 0 | 6 | 0.25 | 30 | 8.25 | 38 | 29.75 | 0.25 | 8.25 | 0% |  | DELIVER UNIT | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | F | RUN FLOW LINE | C |  |  |  | 6 | 10 | 11 | 14 | 11.3333 | 0.66667 | 0.44444 | 11.3333 | 0 | 7 | 30 | 41.6667 | 41.3333 | 53 | 11.6667 | 30 | 41.3333 | 0% |  | RUN FLOW LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | 0 | G | RUN ELECTRIC LINE | C |  |  |  | 3 | 8 | 10 | 12 | 10 | 0.66667 | 0.44444 | 10 | 0 | 8 | 30 | 43 | 40 | 53 | 13 | 30 | 40 | 0% |  | RUN ELECTRIC LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | 1 | H | MOUNT UNIT | D | E |  |  | 3 | 4 | 5 | 12 | 6 | 1.3333 | 1.7778 | 6 | 0 | 9 | 36 | 38 | 42 | 44 | 2 | 36 | 42 | 0% |  | MOUNT UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | 0 | I | INSTALL ELECTRIC MOTOR | H |  |  |  | 2 | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 4 | 0 | 10 | 42 | 49 | 46 | 53 | 7 | 42 | 46 | 0% |  | INSTALL ELECTRIC MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | 1 | J | RUN SUCKER RODS | H |  |  |  | 3 | 4 | 8 | 18 | 9 | 2.3333 | 5.4444 | 9 | 0 | 11 | 42 | 44 | 51 | 53 | 2 | 42 | 51 | 0% |  | RUN SUCKER RODS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | 0 | K | TIE IN, TEST MOTOR | G | I |  |  | 1 | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | 0 | 12 | 46 | 53 | 47.5 | 54.5 | 7 | 46 | 47.5 | 0% |  | TIE IN, TEST MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | 1 | L | NIPPLE UP WELL HEAD | F | J |  |  | 2 | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | 0 | 13 | 51 | 53 | 52.5 | 54.5 | 2 | 51 | 52.5 | 0% |  | NIPPLE UP WELL HEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14 | 1 | M | TEST PUMP | K | L |  |  | 2 | 1 | 4 | 10 | 4.5 | 1.5 | 2.25 | 4.5 | 0 | 14 | 52.5 | 54.5 | 57 | 59 | 2 | 52.5 | 57 | 0% |  | TEST PUMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 | 0 | N | OPEN VALUES | K | L |  |  | 1 | 0.12 | 1 | 2 | 1.02 | 0.31333 | 0.098178 | 1.02 | 0 | 15 | 52.5 | 57.98 | 53.52 | 59 | 5.48 | 52.5 | 53.52 | 0% |  | OPEN VALUES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16 | 1 | End | Activity End |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 57 | 59 | 57 | 59 | 2 | 57 | 57 | 0% |  | Activity End | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16
0
0
0
[10 empty] | 0 | 0 | 0 |  |  |  |  | 2
[10 empty] | 9 | 11 | 19 |  |  |  |  | 2
[10 empty] | 0.25 | 0.25 | 0.25 |  |  |  |  | 0
[10 empty] | 20 | 30 | 40 |  |  |  |  | 0
[10 empty] | 24 | 24 | 24 |  |  |  |  | 11
[10 empty] | 3 | 9 | 9 |  |  |  |  | 0
[10 empty] | 10 | 11 | 14 |  |  |  |  | 0
[10 empty] | 8 | 10 | 12 |  |  |  |  | 0
[10 empty] | 4 | 5 | 12 |  |  |  |  | 0
[10 empty] | 3 | 4 | 5 |  |  |  |  | 0
[10 empty] | 4 | 8 | 18 |  |  |  |  | 0
[10 empty] | 1 | 1 | 4 |  |  |  |  | 0
[10 empty] | 1 | 1 | 4 |  |  |  |  | 0
[10 empty] | 1 | 4 | 10
[10 empty] | 0.12 | 1 | 2
[10 empty] | 0 | 0 | 0

## Pump_Graphics
Project Graphic Pump
| Start(1) | A(2) | D(5) | H(9) | I(10) | K(12) | M(14) | End(16)
|  | B(3) | E(6) |  | J(11) | L(13) | N(15)
|  |  | G(8) |  | F(7)
C(4)

## Pump_Network
Network Pump
Activity on Node Network
Sorted Activity Nodes |  |  |  |  | Sorted Precedence Arcs
[6 empty] | From | To | From | To | Critical
Index | Sort | Name | Level | Depth | Index | Index | Index | Name | Name | Arc
1 | 1 | Start | 0 | 0 | 1 | 1 | 2 | Start | A | 1
2 | 2 | A | 1 | 0 | 2 | 1 | 3 | Start | B | 1
3 | 3 | B | 1 | 1 | 3 | 1 | 4 | Start | C | 1
4 | 4 | C | 1 | 2 | 4 | 2 | 5 | A | D | 1
5 | 5 | D | 2 | 0 | 5 | 3 | 6 | B | E | 1
6 | 6 | E | 2 | 1 | 6 | 4 | 7 | C | F | 1
7 | 7 | F | 2 | 2 | 7 | 4 | 8 | C | G | 1
8 | 8 | G | 2 | 3 | 8 | 5 | 9 | D | H | 1
9 | 9 | H | 3 | 0 | 9 | 6 | 9 | E | H | 1
10 | 10 | I | 4 | 0 | 10 | 7 | 13 | F | L | 1
11 | 11 | J | 4 | 1 | 11 | 8 | 12 | G | K | 1
12 | 12 | K | 5 | 0 | 12 | 9 | 10 | H | I | 1
13 | 13 | L | 5 | 1 | 13 | 9 | 11 | H | J | 1
14 | 14 | M | 6 | 0 | 14 | 10 | 12 | I | K | 1
15 | 15 | N | 6 | 1 | 15 | 11 | 13 | J | L | 1
16 | 16 | End | 7 | 0 | 16 | 12 | 14 | K | M | 1
[5 empty] | 17 | 12 | 15 | K | N | 1
[5 empty] | 18 | 13 | 14 | L | M | 1
[5 empty] | 19 | 13 | 15 | L | N | 1
[5 empty] | 20 | 14 | 16 | M | End | 1
[5 empty] | 21 | 15 | 16 | N | End | 1

## Pump_Schedule
Schedule Pump
Search
Transfer Schedule
|  |  |  | Activities | [5 empty] | Schedule Limits |  |  |  |  | Schedule Decisions |  |  |  | Gantt Chart
Bucket | 1 | Days | [5 empty] | Resources |  | Early | Late | Early | Late |  | Activity | Sched. | Sched. | Perc. | Proj. Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  |  |  | Index | Sort | Name | Description | Crew | Time | Start | Start | Finish | Finish | Slack | Delay | Start | Finish | Finished | Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completion Time |  |  |  | 1 | 1 | Start | Activity Start | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0% | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Due | 59 | Days |  | 2 | 2 | A | POUR SLAB | 4 | 12 | 0 | 2 | 12 | 14 | 2 | 0 | 0 | 12 | 0% | POUR SLAB | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Max Delay | 0 | Days |  | 3 | 3 | B | ORDER PUMP UNIT | 1 | 0.25 | 0 | 29.75 | 0.25 | 30 | 29.75 | 0 | 0 | 0.25 | 0% | ORDER PUMP UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay Unit Cost | 1 | /Days |  | 4 | 4 | C | CUT PATH | 6 | 30 | 0 | 11.6667 | 30 | 41.6667 | 11.6667 | 0 | 0 | 30 | 0% | CUT PATH | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled | 57 | Days |  | 5 | 5 | D | CURE SLAB | 0 | 24 | 12 | 14 | 36 | 38 | 2 | 0 | 12 | 36 | 0% | CURE SLAB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortage | Shortage | 6 | 6 | E | DELIVER UNIT | 0 | 8 | 0.25 | 30 | 8.25 | 38 | 29.75 | 0 | 0.25 | 8.25 | 0% | DELIVER UNIT | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resources | Avail. | Unit Cost | Cost | 7 | 7 | F | RUN FLOW LINE | 6 | 11.3333 | 30 | 41.6667 | 41.3333 | 53 | 11.6667 | 0 | 30 | 41.3333 | 0% | RUN FLOW LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crew | 8 | 1 | 47 | 8 | 8 | G | RUN ELECTRIC LINE | 3 | 10 | 30 | 43 | 40 | 53 | 13 | 0 | 30 | 40 | 0% | RUN ELECTRIC LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 9 | 9 | H | MOUNT UNIT | 3 | 6 | 36 | 38 | 42 | 44 | 2 | 0 | 36 | 42 | 0% | MOUNT UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Costs |  |  |  | 10 | 10 | I | INSTALL ELECTRIC MOTOR | 2 | 4 | 42 | 49 | 46 | 53 | 7 | 0 | 42 | 46 | 0% | INSTALL ELECTRIC MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay | 0 |  |  | 11 | 11 | J | RUN SUCKER RODS | 3 | 9 | 42 | 44 | 51 | 53 | 2 | 0 | 42 | 51 | 0% | RUN SUCKER RODS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shortage | 47 |  |  | 12 | 12 | K | TIE IN, TEST MOTOR | 1 | 1.5 | 46 | 53 | 47.5 | 54.5 | 7 | 0 | 46 | 47.5 | 0% | TIE IN, TEST MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 47 |  |  | 13 | 13 | L | NIPPLE UP WELL HEAD | 2 | 1.5 | 51 | 53 | 52.5 | 54.5 | 2 | 0 | 51 | 52.5 | 0% | NIPPLE UP WELL HEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 14 | 14 | M | TEST PUMP | 2 | 4.5 | 52.5 | 54.5 | 57 | 59 | 2 | 0 | 52.5 | 57 | 0% | TEST PUMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasibility |  |  |  | 15 | 15 | N | OPEN VALUES | 1 | 1.02 | 52.5 | 57.98 | 53.52 | 59 | 5.48 | 0 | 52.5 | 53.52 | 0% | OPEN VALUES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Late | 0 |  |  | 16 | 16 | End | Activity End | 0 | 0 | 57 | 59 | 57 | 59 | 2 | 0 | 57 | 57 | 0% | Activity End | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule | 0 | [16 empty] | Resources
Feasible | TRUE | [16 empty] | Used | Crew | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 12 | 12 | 12 | 12 | 9 | 3 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Available | Crew | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Shortage | Crew | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Shortage Unit Cost | Crew | bar: 1 to 70
[18 empty] | Shortage Cost | Crew | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Shortage Total Cost |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PumpCF
Project PumpCF | [18 empty] | Times(Proj. Hours)
[19 empty] | Due | 59
| Solve | [17 empty] | Critical | 57
[19 empty] | Var. | 12.5
| Change |  | Gantt | [15 empty] | SD. | 3.5355
[19 empty] | On Time Prob. | 0.7142
| Critical |  | Graph | [15 empty] | Slack | 2
[19 empty] | Late | 0
| Update |  | Schedule | [15 empty] | Current | 0
|  | Activity Data | [6 empty] | Cash Flows |  |  | Resources | Activity Time Estimates | [8 empty] | Schedule Limits |  |  |  |  | Schedule Decisions
[9 empty] | Initial | Uniform | Final |  |  | Most |  |  |  |  | Time | Activity |  | Early | Late | Early | Late |  | Sched. | Sched. | Perc.
|  | Critical | Name | Description | Predecessors |  |  | Color | C.F. | C.F. | C.F. | Crews | Min. | Likely | Max. | Mean | S.D. | Var. | Hours | Delay | Sort | Start | Start | Finish | Finish | Slack | Start | Finish | Finished
| 1 | 1 | Start | Activity Start |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0%
| 2 | 1 | A | POUR SLAB |  |  |  |  | 1000 | 80 | 200 | 4 | 9 | 11 | 19 | 12 | 1.6667 | 2.7778 | 12 | 0 | 2 | 0 | 2 | 12 | 14 | 2 | 0 | 12 | 0%
| 3 | 0 | B | ORDER PUMP UNIT |  |  |  |  | 50 | 20 | 0 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0 | 3 | 0 | 29.75 | 0.25 | 30 | 29.75 | 0 | 0.25 | 0%
| 4 | 0 | C | CUT PATH |  |  |  |  | 0 | 120 | 0 | 6 | 20 | 30 | 40 | 30 | 3.3333 | 11.1111 | 30 | 0 | 4 | 0 | 11.6667 | 30 | 41.6667 | 11.6667 | 0 | 30 | 0%
| 5 | 1 | D | CURE SLAB | A |  |  |  | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 0 | 0 | 24 | 0 | 5 | 12 | 14 | 36 | 38 | 2 | 12 | 36 | 0%
| 6 | 0 | E | DELIVER UNIT | B |  |  |  | 3000 | 0 | 0 | 0 | 3 | 9 | 9 | 8 | 1 | 1 | 8 | 0 | 6 | 0.25 | 30 | 8.25 | 38 | 29.75 | 0.25 | 8.25 | 0%
| 7 | 0 | F | RUN FLOW LINE | C |  |  |  | 400 | 120 | 100 | 6 | 10 | 11 | 14 | 11.3333 | 0.66667 | 0.44444 | 11.3333 | 0 | 7 | 30 | 41.6667 | 41.3333 | 53 | 11.6667 | 30 | 41.3333 | 0%
| 8 | 0 | G | RUN ELECTRIC LINE | C |  |  |  | 50 | 60 | 50 | 3 | 8 | 10 | 12 | 10 | 0.66667 | 0.44444 | 10 | 0 | 8 | 30 | 43 | 40 | 53 | 13 | 30 | 40 | 0%
| 9 | 1 | H | MOUNT UNIT | D | E |  |  | 0 | 60 | 0 | 3 | 4 | 5 | 12 | 6 | 1.3333 | 1.7778 | 6 | 0 | 9 | 36 | 38 | 42 | 44 | 2 | 36 | 42 | 0%
| 10 | 0 | I | INSTALL ELECTRIC MOTOR | H |  |  |  | 1000 | 40 | 250 | 2 | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 4 | 0 | 10 | 42 | 49 | 46 | 53 | 7 | 42 | 46 | 0%
| 11 | 1 | J | RUN SUCKER RODS | H |  |  |  | 500 | 60 | 0 | 3 | 4 | 8 | 18 | 9 | 2.3333 | 5.4444 | 9 | 0 | 11 | 42 | 44 | 51 | 53 | 2 | 42 | 51 | 0%
| 12 | 0 | K | TIE IN, TEST MOTOR | G | I |  |  | 300 | 20 | 100 | 1 | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | 0 | 12 | 46 | 53 | 47.5 | 54.5 | 7 | 46 | 47.5 | 0%
| 13 | 1 | L | NIPPLE UP WELL HEAD | F | J |  |  | 300 | 40 | 100 | 2 | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | 0 | 13 | 51 | 53 | 52.5 | 54.5 | 2 | 51 | 52.5 | 0%
| 14 | 1 | M | TEST PUMP | K | L |  |  | 0 | 40 | 500 | 2 | 1 | 4 | 10 | 4.5 | 1.5 | 2.25 | 4.5 | 0 | 14 | 52.5 | 54.5 | 57 | 59 | 2 | 52.5 | 57 | 0%
| 15 | 0 | N | OPEN VALUES | K | L |  |  | 0 | 20 | 0 | 1 | 0.12 | 1 | 2 | 1.02 | 0.31333 | 0.098178 | 1.02 | 0 | 15 | 52.5 | 57.98 | 53.52 | 59 | 5.48 | 52.5 | 53.52 | 0%
| 16 | 1 | End | Activity End |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 57 | 59 | 57 | 59 | 2 | 57 | 57 | 0%
16
0
0
21
2
0
6
0
11
2
3
0
0
0
0
1
0

## PumpCF_Network
Network PumpCF
Activity on Node Network
Sorted Activity Nodes |  |  |  |  | Sorted Precedence Arcs
[6 empty] | From | To | From | To | Critical
Index | Sort | Name | Level | Depth | Index | Index | Index | Name | Name | Arc
1 | 1 | Start | 0 | 0 | 1 | 1 | 2 | Start | A | 1
2 | 2 | A | 1 | 0 | 2 | 1 | 3 | Start | B | 1
3 | 3 | B | 1 | 1 | 3 | 1 | 4 | Start | C | 1
4 | 4 | C | 1 | 2 | 4 | 2 | 5 | A | D | 1
5 | 5 | D | 2 | 0 | 5 | 3 | 6 | B | E | 1
6 | 6 | E | 2 | 1 | 6 | 4 | 7 | C | F | 1
7 | 7 | F | 2 | 2 | 7 | 4 | 8 | C | G | 1
8 | 8 | G | 2 | 3 | 8 | 5 | 9 | D | H | 1
9 | 9 | H | 3 | 0 | 9 | 6 | 9 | E | H | 1
10 | 10 | I | 4 | 0 | 10 | 7 | 13 | F | L | 1
11 | 11 | J | 4 | 1 | 11 | 8 | 12 | G | K | 1
12 | 12 | K | 5 | 0 | 12 | 9 | 10 | H | I | 1
13 | 13 | L | 5 | 1 | 13 | 9 | 11 | H | J | 1
14 | 14 | M | 6 | 0 | 14 | 10 | 12 | I | K | 1
15 | 15 | N | 6 | 1 | 15 | 11 | 13 | J | L | 1
16 | 16 | End | 7 | 0 | 16 | 12 | 14 | K | M | 1
[5 empty] | 17 | 12 | 15 | K | N | 1
[5 empty] | 18 | 13 | 14 | L | M | 1
[5 empty] | 19 | 13 | 15 | L | N | 1
[5 empty] | 20 | 14 | 16 | M | End | 1
[5 empty] | 21 | 15 | 16 | N | End | 1

## PumpCF_Schedule
Schedule PumpCF
Search
Transfer Schedule
Cash Flow
|  |  |  | Activities | [8 empty] | Schedule Limits |  |  |  |  | Schedule Decisions |  |  |  | Gantt Chart
Bucket | 1 | Hours | [5 empty] | Initial | Uniform | Final | Resources |  | Early | Late | Early | Late |  | Activity | Sched. | Sched. | Perc. | Proj. Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  |  |  | Index | Sort | Name | Description | C.F. | C.F. | C.F. | Crews | Time | Start | Start | Finish | Finish | Slack | Delay | Start | Finish | Finished | Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completion Time |  |  |  | 1 | 1 | Start | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Due | 59 | Hours |  | 2 | 2 | A | POUR SLAB | 1000 | 80 | 200 | 4 | 12 | 0 | 0 | 14 | 14 | 0 | 2 | 2 | 14 | 0% | POUR SLAB | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Max Delay | 0 | Hours |  | 3 | 3 | B | ORDER PUMP UNIT | 50 | 20 | 0 | 1 | 0.25 | 0 | 0.75 | 29.25 | 30 | 0.75 | 29 | 29 | 29.25 | 0% | ORDER PUMP UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay Unit Cost | 1 | /Hours |  | 4 | 4 | C | CUT PATH | 0 | 120 | 0 | 6 | 30 | 0 | 1.6667 | 30 | 31.6667 | 1.6667 | 0 | 0 | 30 | 0% | CUT PATH | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled | 59 | Hours |  | 5 | 5 | D | CURE SLAB | 0 | 0 | 0 | 0 | 24 | 14 | 14 | 38 | 38 | 0 | 0 | 14 | 38 | 0% | CURE SLAB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortage | Shortage | 6 | 6 | E | DELIVER UNIT | 3000 | 0 | 0 | 0 | 8 | 29.25 | 30 | 37.25 | 38 | 0.75 | 0 | 29.25 | 37.25 | 0% | DELIVER UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resources | Avail. | Unit Cost | Cost | 7 | 7 | F | RUN FLOW LINE | 400 | 120 | 100 | 6 | 11.3333 | 30 | 31.6667 | 51.3333 | 53 | 1.6667 | 10 | 40 | 51.3333 | 0% | RUN FLOW LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crews | 8 | 10 | 390 | 8 | 8 | G | RUN ELECTRIC LINE | 50 | 60 | 50 | 3 | 10 | 30 | 43 | 40 | 53 | 13 | 0 | 30 | 40 | 0% | RUN ELECTRIC LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 9 | 9 | H | MOUNT UNIT | 0 | 60 | 0 | 3 | 6 | 38 | 38 | 44 | 44 | 0 | 0 | 38 | 44 | 0% | MOUNT UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Costs |  |  |  | 10 | 10 | I | INSTALL ELECTRIC MOTOR | 1000 | 40 | 250 | 2 | 4 | 44 | 44 | 53 | 53 | 0 | 5 | 49 | 53 | 0% | INSTALL ELECTRIC MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay | 0 |  |  | 11 | 11 | J | RUN SUCKER RODS | 500 | 60 | 0 | 3 | 9 | 44 | 44 | 53 | 53 | 0 | 0 | 44 | 53 | 0% | RUN SUCKER RODS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shortage | 390 |  |  | 12 | 12 | K | TIE IN, TEST MOTOR | 300 | 20 | 100 | 1 | 1.5 | 53 | 53 | 54.5 | 54.5 | 0 | 0 | 53 | 54.5 | 0% | TIE IN, TEST MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 390 |  |  | 13 | 13 | L | NIPPLE UP WELL HEAD | 300 | 40 | 100 | 2 | 1.5 | 53 | 53 | 54.5 | 54.5 | 0 | 0 | 53 | 54.5 | 0% | NIPPLE UP WELL HEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 14 | 14 | M | TEST PUMP | 0 | 40 | 500 | 2 | 4.5 | 54.5 | 54.5 | 59 | 59 | 0 | 0 | 54.5 | 59 | 0% | TEST PUMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasibility |  |  |  | 15 | 15 | N | OPEN VALUES | 0 | 20 | 0 | 1 | 1.02 | 54.5 | 54.98 | 58.52 | 59 | 0.48 | 3 | 57.5 | 58.52 | 0% | OPEN VALUES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Late | 0 |  |  | 16 | 16 | End | Activity End | 0 | 0 | 0 | 0 | 0 | 59 | 59 | 59 | 59 | 0 | 0 | 59 | 59 | 0% | Activity End | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule | 0 | [19 empty] | Resources
Feasible | TRUE | [19 empty] | Used | Crews | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 6 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 11 | 11 | 5 | 5 | 3 | 2 | 2 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | Available | Crews | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Flow | [20 empty] | Shortage | Crews | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest/Hours | 0.016% | [19 empty] | Shortage Unit Cost | Crews | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Interest/Bucket | 0.016% | [19 empty] | Shortage Cost | Crews | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Present Value | 16029.8476 | [19 empty] | Shortage Total Cost |  | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uniform Value/Hours | 272.9985
[21 empty] | Cumulative Cash Flow |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
[21 empty] | Initial | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 4050 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4500 | 4500 | 4500 | 4500 | 5000 | 5000 | 5000 | 5000 | 5000 | 6000 | 6000 | 6000 | 6000 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600
[21 empty] | Uniform | 0 | 120 | 240 | 460 | 680 | 900 | 1120 | 1340 | 1560 | 1780 | 2000 | 2220 | 2440 | 2660 | 2880 | 3000 | 3120 | 3240 | 3360 | 3480 | 3600 | 3720 | 3840 | 3960 | 4080 | 4200 | 4320 | 4440 | 4560 | 4680 | 4800 | 4860 | 4920 | 4980 | 5040 | 5100 | 5160 | 5220 | 5280 | 5400 | 5520 | 5710 | 5900 | 6090 | 6280 | 6470 | 6660 | 6850 | 7040 | 7230 | 7480 | 7730 | 7830 | 7930 | 7990 | 8030 | 8070 | 8110 | 8170 | 8210 | 8210 | 8210 | 8210 | 8210 | 8210 | 8210 | 8210 | 8210 | 8210 | 8210 | 8210
[21 empty] | Final | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 350 | 350 | 600 | 800 | 800 | 800 | 800 | 800 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
25% | /year | [19 empty] | Total | 0 | 120 | 240 | 1460 | 1680 | 1900 | 2120 | 2340 | 2560 | 2780 | 3000 | 3220 | 3440 | 3660 | 3880 | 4200 | 4320 | 4440 | 4560 | 4680 | 4800 | 4920 | 5040 | 5160 | 5280 | 5400 | 5520 | 5640 | 5760 | 5880 | 9050 | 9160 | 9220 | 9280 | 9340 | 9400 | 9460 | 9520 | 9580 | 9700 | 9820 | 10460 | 10650 | 10840 | 11030 | 11720 | 11910 | 12100 | 12290 | 12480 | 13730 | 13980 | 14180 | 14280 | 15190 | 15430 | 15470 | 15510 | 15570 | 15610 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110
0.125% | /day | [19 empty] | Bucket Cash Flow |  | 120 | 120 | 1220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 320 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 3170 | 110 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 120 | 120 | 640 | 190 | 190 | 190 | 690 | 190 | 190 | 190 | 190 | 1250 | 250 | 200 | 100 | 910 | 240 | 40 | 40 | 60 | 40 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.01562% | /hour
[21 empty] | Cumulative Cash Flow | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
[21 empty] | Early | 0 | 4270 | 4490 | 4710 | 4930 | 5150 | 5370 | 5590 | 5810 | 6030 | 6250 | 6470 | 6690 | 7010 | 7130 | 7250 | 7370 | 7490 | 7610 | 7730 | 7850 | 7970 | 8090 | 8210 | 8330 | 8450 | 8570 | 8690 | 8810 | 8930 | 9050 | 9690 | 9880 | 10070 | 10260 | 10450 | 10640 | 10920 | 11200 | 11480 | 11760 | 12000 | 12160 | 13760 | 13860 | 13960 | 14060 | 14690 | 14850 | 14910 | 14970 | 15030 | 15370 | 15530 | 15570 | 15610 | 15650 | 15690 | 16190 | 16190 | 16190 | 16190 | 16190 | 16190 | 16190 | 16190 | 16190 | 16190 | 16190 | 16190 | 16190
[21 empty] | Current | 0 | 120 | 240 | 1460 | 1680 | 1900 | 2120 | 2340 | 2560 | 2780 | 3000 | 3220 | 3440 | 3660 | 3880 | 4200 | 4320 | 4440 | 4560 | 4680 | 4800 | 4920 | 5040 | 5160 | 5280 | 5400 | 5520 | 5640 | 5760 | 5880 | 9050 | 9160 | 9220 | 9280 | 9340 | 9400 | 9460 | 9520 | 9580 | 9700 | 9820 | 10460 | 10650 | 10840 | 11030 | 11720 | 11910 | 12100 | 12290 | 12480 | 13730 | 13980 | 14180 | 14280 | 15190 | 15430 | 15470 | 15510 | 15570 | 15610 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110 | 16110
[21 empty] | Late | 0 | 0 | 0 | 1080 | 1160 | 1240 | 1320 | 1400 | 1480 | 1560 | 1640 | 1720 | 1940 | 2160 | 2380 | 2700 | 2820 | 2940 | 3060 | 3180 | 3300 | 3420 | 3540 | 3660 | 3780 | 3900 | 4020 | 4140 | 4260 | 4380 | 4570 | 7690 | 7810 | 7930 | 8050 | 8170 | 8290 | 8410 | 8530 | 8720 | 8910 | 9100 | 9690 | 9880 | 10210 | 10990 | 11270 | 11550 | 11830 | 12110 | 13450 | 13790 | 14130 | 14470 | 15530 | 15770 | 15810 | 15850 | 15910 | 15970 | 16470 | 16470 | 16470 | 16470 | 16470 | 16470 | 16470 | 16470 | 16470 | 16470 | 16470
Back

## PumpVAR
Project PumpVAR | [17 empty] | Times(Proj. Hours) | [11 empty] | Gantt Parmeters
[18 empty] | Due | 59 | [9 empty] | Bucket | 1
| Solve | [16 empty] | Critical | 57.25 | [9 empty] | Start | 0
[18 empty] | Var. | 10.7222 | [9 empty] | Horizon | 59
| Change |  | Gantt | [14 empty] | SD. | 3.2745 | [9 empty] | Extra | 10
[18 empty] | On Time Prob. | 0.70348
| Critical |  | Graph | [14 empty] | Slack | 1.75
[18 empty] | Late | 0
| Update |  | Schedule | [14 empty] | Current | 0
|  | Activity Data | [5 empty] | Cash Flows |  |  | Resources | Activity Time Estimates | [8 empty] | Schedule Limits |  |  |  |  | Schedule Decisions |  |  |  | Gantt Chart
[8 empty] | Initial | Uniform | Final |  |  | Most |  |  |  |  | Time | Activity |  | Early | Late | Early | Late |  | Sched. | Sched. | Perc. |  | Proj. Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69
|  | Critical | Name | Description | Predecessors |  | Color | C.F. | C.F. | C.F. | Crews | Min. | Likely | Max. | Mean | S.D. | Var. | Hours | Delay | Sort | Start | Start | Finish | Finish | Slack | Start | Finish | Finished |  | Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 1 | Start | Activity Start |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1.75 | 0 | 1.75 | 1.75 | 0 | 0 | 0% |  | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 0 | A | POUR SLAB |  |  |  | 1000 | 80 | 200 | 4 | 9 | 11 | 19 | 12 | 1.6667 | 2.7778 | 12 | 0 | 2 | 0 | 2 | 12 | 14 | 2 | 0 | 12 | 0% |  | POUR SLAB | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 1 | B | ORDER PUMP UNIT |  |  |  | 50 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0.25 | 28 | 3 | 0 | 1.75 | 28.25 | 30 | 1.75 | 28 | 28.25 | 0% |  | ORDER PUMP UNIT | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | C | CUT PATH |  |  |  | 0 | 120 | 0 | 6 | 20 | 30 | 40 | 30 | 3.3333 | 11.1111 | 30 | 0 | 4 | 0 | 2 | 30 | 32 | 2 | 0 | 30 | 0% |  | CUT PATH | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | 0 | D | CURE SLAB | A |  |  | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 0 | 0 | 24 | 0 | 5 | 12 | 14 | 36 | 38 | 2 | 12 | 36 | 0% |  | CURE SLAB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 1 | E | DELIVER UNIT | B |  |  | 3000 | 0 | 0 | 0 | 3 | 9 | 9 | 8 | 1 | 1 | 8 | 0 | 6 | 28.25 | 30 | 36.25 | 38 | 1.75 | 28.25 | 36.25 | 0% |  | DELIVER UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | F | RUN FLOW LINE | C |  |  | 400 | 120 | 100 | 6 | 10 | 11 | 14 | 11.3333 | 0.66667 | 0.44444 | 11.3333 | 0 | 7 | 30 | 41.6667 | 41.3333 | 53 | 11.6667 | 30 | 41.3333 | 0% |  | RUN FLOW LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | 0 | G | RUN ELECTRIC LINE | C |  |  | 50 | 60 | 50 | 3 | 8 | 10 | 12 | 10 | 0.66667 | 0.44444 | 10 | 11 | 8 | 30 | 32 | 51 | 53 | 2 | 41 | 51 | 0% |  | RUN ELECTRIC LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | 1 | H | MOUNT UNIT | D | E |  | 0 | 0 | 0 | 0 | 4 | 5 | 12 | 6 | 1.3333 | 1.7778 | 6 | 0 | 9 | 36.25 | 38 | 42.25 | 44 | 1.75 | 36.25 | 42.25 | 0% |  | MOUNT UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | 0 | I | INSTALL ELECTRIC MOTOR | H |  |  | 1000 | 40 | 250 | 2 | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 4 | 0 | 10 | 42.25 | 49 | 46.25 | 53 | 6.75 | 42.25 | 46.25 | 0% |  | INSTALL ELECTRIC MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | 1 | J | RUN SUCKER RODS | H |  |  | 500 | 60 | 0 | 3 | 4 | 8 | 18 | 9 | 2.3333 | 5.4444 | 9 | 0 | 11 | 42.25 | 44 | 51.25 | 53 | 1.75 | 42.25 | 51.25 | 0% |  | RUN SUCKER RODS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | 0 | K | TIE IN, TEST MOTOR | G | I |  | 300 | 20 | 100 | 1 | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | 0 | 12 | 51 | 53 | 52.5 | 54.5 | 2 | 51 | 52.5 | 0% |  | TIE IN, TEST MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | 1 | L | NIPPLE UP WELL HEAD | F | J |  | 300 | 40 | 100 | 2 | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | 0 | 13 | 51.25 | 53 | 52.75 | 54.5 | 1.75 | 51.25 | 52.75 | 0% |  | NIPPLE UP WELL HEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14 | 1 | M | TEST PUMP | K | L |  | 0 | 40 | 500 | 2 | 1 | 4 | 10 | 4.5 | 1.5 | 2.25 | 4.5 | 0 | 14 | 52.75 | 54.5 | 57.25 | 59 | 1.75 | 52.75 | 57.25 | 0% |  | TEST PUMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 | 0 | N | OPEN VALUES | K | L |  | 0 | 20 | 0 | 1 | 0.12 | 1 | 2 | 1.02 | 0.31333 | 0.098178 | 1.02 | 3 | 15 | 52.75 | 54.98 | 56.77 | 59 | 2.23 | 55.75 | 56.77 | 0% |  | OPEN VALUES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16 | 1 | End | Activity End |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 57.25 | 59 | 57.25 | 59 | 1.75 | 57.25 | 57.25 | 0% |  | Activity End | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 16 | [18 empty] | VA | 0 | 57.25 | 0% |  | Rent Buildings | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | VB | 0 | 36 | 0% |  | Concrete Equipment Rental | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variable Activity Data |  |  | From | To |  | Initial | Uniform | Final | Resources | [13 empty] | VC | 41 | 52.5 | 0% |  | Registered Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Name | Description | Activity | Activity | Color | C.F. | C.F. | C.F. | Crews | [13 empty] | VD | 28 | 42.25 | 0% |  | Outsource Pump Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 | VA | Rent Buildings | Start | End |  | 500 | 30 | -500 | 1 | [13 empty] | VE | 0 | 57.25 | 0% |  | Constuction Loan/Manag. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | VB | Concrete Equipment Rental | A | D |  | 0 | 10 | 0 | 0 | [13 empty] | VF | 12 | 36 | 0% |  | Payment 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 | VC | Registered Engineer | G | K |  | 200 | 50 | 0 | 0 | [13 empty] | VG | 42.25 | 46.25 | 0% |  | Payment 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 | VD | Outsource Pump Installation | B | H |  | 200 | 20 | 300 | 1 | [13 empty] | VH | 55.75 | 57.25 | 0% |  | Final Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 | VE | Constuction Loan/Manag. | Start | End |  | -10000 | 80 | 10500 | 0
|  | 6 | VF | Payment 1 | D | D |  | 0 | 0 | -9000 | 0
|  | 7 | VG | Payment 2 | I | I |  | 0 | 0 | -9000 | 0
|  | 8 | VH | Final Payment | N | End |  | 0 | 0 | -9000 | 0

## PumpVAR_Schedule
Schedule PumpVAR
Search
Transfer Schedule
Cash Flow
|  |  |  | Activities | [8 empty] | Schedule Limits |  |  |  |  | Schedule Decisions |  |  |  | Gantt Chart
Bucket | 1 | Hours | [5 empty] | Initial | Uniform | Final | Resources |  | Early | Late | Early | Late |  | Activity | Sched. | Sched. | Perc. | Proj. Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  |  |  | Index | Sort | Name | Description | C.F. | C.F. | C.F. | Crews | Time | Start | Start | Finish | Finish | Slack | Delay | Start | Finish | Finished | Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completion Time |  |  |  | 1 | 1 | Start | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 1.75 | 1.75 | 0 | 0 | 0 | 0% | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Due | 59 | Hours |  | 2 | 2 | A | POUR SLAB | 1000 | 80 | 200 | 4 | 12 | 0 | 2 | 12 | 14 | 2 | 0 | 0 | 12 | 0% | POUR SLAB | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Max Delay | 0 | Hours |  | 3 | 3 | B | ORDER PUMP UNIT | 50 | 0 | 0 | 0 | 0.25 | 0 | 1.75 | 28.25 | 30 | 1.75 | 28 | 28 | 28.25 | 0% | ORDER PUMP UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay Unit Cost | 1 | /Hours |  | 4 | 4 | C | CUT PATH | 0 | 120 | 0 | 6 | 30 | 0 | 2 | 30 | 32 | 2 | 0 | 0 | 30 | 0% | CUT PATH | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled | 57.25 | Hours |  | 5 | 5 | D | CURE SLAB | 0 | 0 | 0 | 0 | 24 | 12 | 14 | 36 | 38 | 2 | 0 | 12 | 36 | 0% | CURE SLAB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortage | Shortage | 6 | 6 | E | DELIVER UNIT | 3000 | 0 | 0 | 0 | 8 | 28.25 | 30 | 36.25 | 38 | 1.75 | 0 | 28.25 | 36.25 | 0% | DELIVER UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resources | Avail. | Unit Cost | Cost | 7 | 7 | F | RUN FLOW LINE | 400 | 120 | 100 | 6 | 11.3333 | 30 | 41.6667 | 41.3333 | 53 | 11.6667 | 0 | 30 | 41.3333 | 0% | RUN FLOW LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crews | 8 | 10 | 400 | 8 | 8 | G | RUN ELECTRIC LINE | 50 | 60 | 50 | 3 | 10 | 30 | 32 | 51 | 53 | 2 | 11 | 41 | 51 | 0% | RUN ELECTRIC LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 9 | 9 | H | MOUNT UNIT | 0 | 0 | 0 | 0 | 6 | 36.25 | 38 | 42.25 | 44 | 1.75 | 0 | 36.25 | 42.25 | 0% | MOUNT UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Costs |  |  |  | 10 | 10 | I | INSTALL ELECTRIC MOTOR | 1000 | 40 | 250 | 2 | 4 | 42.25 | 49 | 46.25 | 53 | 6.75 | 0 | 42.25 | 46.25 | 0% | INSTALL ELECTRIC MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay | 0 |  |  | 11 | 11 | J | RUN SUCKER RODS | 500 | 60 | 0 | 3 | 9 | 42.25 | 44 | 51.25 | 53 | 1.75 | 0 | 42.25 | 51.25 | 0% | RUN SUCKER RODS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shortage | 400 |  |  | 12 | 12 | K | TIE IN, TEST MOTOR | 300 | 20 | 100 | 1 | 1.5 | 51 | 53 | 52.5 | 54.5 | 2 | 0 | 51 | 52.5 | 0% | TIE IN, TEST MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 400 |  |  | 13 | 13 | L | NIPPLE UP WELL HEAD | 300 | 40 | 100 | 2 | 1.5 | 51.25 | 53 | 52.75 | 54.5 | 1.75 | 0 | 51.25 | 52.75 | 0% | NIPPLE UP WELL HEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 14 | 14 | M | TEST PUMP | 0 | 40 | 500 | 2 | 4.5 | 52.75 | 54.5 | 57.25 | 59 | 1.75 | 0 | 52.75 | 57.25 | 0% | TEST PUMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasibility |  |  |  | 15 | 15 | N | OPEN VALUES | 0 | 20 | 0 | 1 | 1.02 | 52.75 | 54.98 | 56.77 | 59 | 2.23 | 3 | 55.75 | 56.77 | 0% | OPEN VALUES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Late | 0 |  |  | 16 | 16 | End | Activity End | 0 | 0 | 0 | 0 | 0 | 57.25 | 59 | 57.25 | 59 | 1.75 | 0 | 57.25 | 57.25 | 0% | Activity End | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule | 0 |  |  | 17 | 1 | VA | Rent Buildings | 500 | 30 | -500 | 1 | 57.25 | [6 empty] | 0 | 57.25 | 0% | Rent Buildings | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasible | TRUE |  |  | 18 | 2 | VB | Concrete Equipment Rental | 0 | 10 | 0 | 0 | 36 | [6 empty] | 0 | 36 | 0% | Concrete Equipment Rental | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 19 | 3 | VC | Registered Engineer | 200 | 50 | 0 | 0 | 11.5 | [6 empty] | 41 | 52.5 | 0% | Registered Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Flow |  |  |  | 20 | 4 | VD | Outsource Pump Installation | 200 | 20 | 300 | 1 | 14.25 | [6 empty] | 28 | 42.25 | 0% | Outsource Pump Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest/Hours | 0.016% |  |  | 21 | 5 | VE | Constuction Loan/Manag. | -10000 | 80 | 10500 | 0 | 57.25 | [6 empty] | 0 | 57.25 | 0% | Constuction Loan/Manag. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest/Bucket | 0.016% |  |  | 22 | 6 | VF | Payment 1 | 0 | 0 | -9000 | 0 | 24 | [6 empty] | 12 | 36 | 0% | Payment 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Present Value | -2578.9995 |  |  | 23 | 7 | VG | Payment 2 | 0 | 0 | -9000 | 0 | 4 | [6 empty] | 42.25 | 46.25 | 0% | Payment 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uniform Value/Hours | -45.2583 |  |  | 24 | 8 | VH | Final Payment | 0 | 0 | -9000 | 0 | 1.5 | [6 empty] | 55.75 | 57.25 | 0% | Final Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resources
[21 empty] | Used | Crews | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 4 | 3 | 3 | 3 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | Available | Crews | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | Shortage | Crews | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | Shortage Unit Cost | Crews | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
[21 empty] | Shortage Cost | Crews | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | Shortage Total Cost |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | Cumulative Cash Flow |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
[21 empty] | Initial | 0 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -8500 | -5250 | -5250 | -4850 | -4850 | -4850 | -4850 | -4850 | -4850 | -4850 | -4850 | -4850 | -4850 | -4850 | -4600 | -3100 | -3100 | -3100 | -3100 | -3100 | -3100 | -3100 | -3100 | -3100 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500 | -2500
[21 empty] | Uniform | 0 | 350 | 700 | 1050 | 1400 | 1750 | 2100 | 2450 | 2800 | 3150 | 3500 | 3850 | 4200 | 4440 | 4680 | 4920 | 5160 | 5400 | 5640 | 5880 | 6120 | 6360 | 6600 | 6840 | 7080 | 7320 | 7560 | 7800 | 8040 | 8300 | 8560 | 8820 | 9080 | 9340 | 9600 | 9860 | 10120 | 10370 | 10620 | 10870 | 11120 | 11370 | 11610 | 11940 | 12270 | 12600 | 12930 | 13210 | 13490 | 13770 | 14050 | 14330 | 14550 | 14700 | 14850 | 15000 | 15170 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320 | 15320
[21 empty] | Final | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | -8800 | -8800 | -8800 | -8800 | -8800 | -8700 | -8400 | -8400 | -8400 | -8400 | -17150 | -17150 | -17150 | -17150 | -17150 | -17100 | -16900 | -16900 | -16900 | -16900 | -16900 | -15400 | -15400 | -15400 | -15400 | -15400 | -15400 | -15400 | -15400 | -15400 | -15400 | -15400 | -15400 | -15400
[21 empty] | Total | 0 | -8150 | -7800 | -7450 | -7100 | -6750 | -6400 | -6050 | -5700 | -5350 | -5000 | -4650 | -4300 | -3860 | -3620 | -3380 | -3140 | -2900 | -2660 | -2420 | -2180 | -1940 | -1700 | -1460 | -1220 | -980 | -740 | -500 | -260 | 3250 | 3510 | 4170 | 4430 | 4690 | 4950 | 5210 | 5470 | -3280 | -3030 | -2780 | -2530 | -2280 | -1690 | 440 | 770 | 1100 | 1430 | -7040 | -6760 | -6480 | -6200 | -5920 | -5050 | -4700 | -4550 | -4400 | -4230 | -4080 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580
[21 empty] | Bucket Cash Flow |  | -8150 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 440 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 3510 | 260 | 660 | 260 | 260 | 260 | 260 | 260 | -8750 | 250 | 250 | 250 | 250 | 590 | 2130 | 330 | 330 | 330 | -8470 | 280 | 280 | 280 | 280 | 870 | 350 | 150 | 150 | 170 | 150 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | Cumulative Cash Flow | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
[21 empty] | Early | 0 | -4870 | -4490 | -4110 | -3730 | -3350 | -2970 | -2590 | -2210 | -1830 | -1450 | -1070 | -690 | -230 | 30 | 290 | 550 | 810 | 1070 | 1330 | 1590 | 1850 | 2110 | 2370 | 2630 | 2890 | 3150 | 3410 | 3670 | 3930 | 4190 | 5240 | 5640 | 6040 | 6440 | 6840 | 7240 | -1370 | -980 | -590 | -200 | 150 | 430 | 2490 | 2750 | 3010 | 3270 | -4940 | -4670 | -4500 | -4330 | -4160 | -3710 | -3440 | -3290 | -3140 | -2990 | -2840 | -1340 | -1340 | -1340 | -1340 | -1340 | -1340 | -1340 | -1340 | -1340 | -1340 | -1340 | -1340 | -1340
[21 empty] | Current | 0 | -8150 | -7800 | -7450 | -7100 | -6750 | -6400 | -6050 | -5700 | -5350 | -5000 | -4650 | -4300 | -3860 | -3620 | -3380 | -3140 | -2900 | -2660 | -2420 | -2180 | -1940 | -1700 | -1460 | -1220 | -980 | -740 | -500 | -260 | 3250 | 3510 | 4170 | 4430 | 4690 | 4950 | 5210 | 5470 | -3280 | -3030 | -2780 | -2530 | -2280 | -1690 | 440 | 770 | 1100 | 1430 | -7040 | -6760 | -6480 | -6200 | -5920 | -5050 | -4700 | -4550 | -4400 | -4230 | -4080 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580 | -2580
[21 empty] | Late | 0 | 0 | 0 | -8300 | -8100 | -7900 | -7700 | -7500 | -7300 | -7100 | -6900 | -6700 | -6350 | -6000 | -5650 | -5210 | -4970 | -4730 | -4490 | -4250 | -4010 | -3770 | -3530 | -3290 | -3050 | -2810 | -2570 | -2330 | -2090 | -1850 | -1340 | 1920 | 2180 | 2440 | 2700 | 2960 | 3220 | 3480 | 3740 | -5010 | -4760 | -4510 | -3860 | -3610 | -2970 | -1720 | -1270 | -820 | -370 | 80 | 1590 | 2100 | 2610 | 3120 | -4660 | -4310 | -4160 | -4010 | -3840 | -3670 | -2170 | -2170 | -2170 | -2170 | -2170 | -2170 | -2170 | -2170 | -2170 | -2170 | -2170
Back

## PumpVAR_Network
Network PumpVAR
Activity on Node Network
Sorted Activity Nodes |  |  |  |  | Sorted Precedence Arcs
[6 empty] | From | To | From | To | Critical
Index | Sort | Name | Level | Depth | Index | Index | Index | Name | Name | Arc
1 | 1 | Start | 0 | 0 | 1 | 1 | 2 | Start | A | 1
2 | 2 | A | 1 | 0 | 2 | 1 | 3 | Start | B | 1
3 | 3 | B | 1 | 1 | 3 | 1 | 4 | Start | C | 1
4 | 4 | C | 1 | 2 | 4 | 2 | 5 | A | D | 1
5 | 5 | D | 2 | 0 | 5 | 3 | 6 | B | E | 1
6 | 6 | E | 2 | 1 | 6 | 4 | 7 | C | F | 1
7 | 7 | F | 2 | 2 | 7 | 4 | 8 | C | G | 1
8 | 8 | G | 2 | 3 | 8 | 5 | 9 | D | H | 1
9 | 9 | H | 3 | 0 | 9 | 6 | 9 | E | H | 1
10 | 10 | I | 4 | 0 | 10 | 7 | 13 | F | L | 1
11 | 11 | J | 4 | 1 | 11 | 8 | 12 | G | K | 1
12 | 12 | K | 5 | 0 | 12 | 9 | 10 | H | I | 1
13 | 13 | L | 5 | 1 | 13 | 9 | 11 | H | J | 1
14 | 14 | M | 6 | 0 | 14 | 10 | 12 | I | K | 1
15 | 15 | N | 6 | 1 | 15 | 11 | 13 | J | L | 1
16 | 16 | End | 7 | 0 | 16 | 12 | 14 | K | M | 1
[5 empty] | 17 | 12 | 15 | K | N | 1
[5 empty] | 18 | 13 | 14 | L | M | 1
[5 empty] | 19 | 13 | 15 | L | N | 1
[5 empty] | 20 | 14 | 16 | M | End | 1
[5 empty] | 21 | 15 | 16 | N | End | 1

## PumpRV
Project PumpRV | [14 empty] | Times(Proj. Hours)
[15 empty] | Due | 59
| Solve |  | Simulate | [11 empty] | Critical | 61
[15 empty] | Var. | 20.5
| Change |  | Gantt | [11 empty] | SD. | 4.5277
[15 empty] | On Time Prob. | 0.32934
| Critical |  | Graph | [11 empty] | Slack | 0
[8 empty] | Estimate | Mean | [5 empty] | Late | 2
| Update |  | Schedule |  |  |  |  | Percentile | 40% | [5 empty] | Current | 0
|  | Activity Data | [5 empty] | Activity Time Estimates | [9 empty] | Schedule Limits |  |  |  |  | Schedule Decisions
[10 empty] | Most |  |  |  |  | Time | Activity |  | Early | Late | Early | Late |  | Sched. | Sched. | Perc.
|  | Critical | Name | Description | Predecessors |  | Color | Dist. | Min. | Likely | Max. | Mean | S.D. | Var. | Hours | Delay | Sort | Start | Start | Finish | Finish | Slack | Start | Finish | Finished
| 1 | 1 | Start | Activity Start |  |  |  | Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| 2 | 1 | A | POUR SLAB |  |  |  | Tri | 9 | 11 | 19 | 13 | 2.1602 | 4.6667 | 13 | 0 | 2 | 0 | 0 | 13 | 13 | 0 | 0 | 13 | 0%
| 3 | 0 | B | ORDER PUMP UNIT |  |  |  | Tri | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0 | 3 | 0 | 29.75 | 0.25 | 30 | 29.75 | 0 | 0.25 | 0%
| 4 | 0 | C | CUT PATH |  |  |  | Tri | 20 | 30 | 40 | 30 | 4.0825 | 16.6667 | 30 | 0 | 4 | 0 | 12.3333 | 30 | 42.3333 | 12.3333 | 0 | 30 | 0%
| 5 | 1 | D | CURE SLAB | A |  |  | Tri | 24 | 24 | 24 | 24 | 0 | 0 | 24 | 0 | 5 | 13 | 13 | 37 | 37 | 0 | 13 | 37 | 0%
| 6 | 0 | E | DELIVER UNIT | B |  |  | Tri | 3 | 9 | 9 | 7 | 1.4142 | 2 | 7 | 0 | 6 | 0.25 | 30 | 7.25 | 37 | 29.75 | 0.25 | 7.25 | 0%
| 7 | 0 | F | RUN FLOW LINE | C |  |  | Tri | 10 | 11 | 14 | 11.6667 | 0.84984 | 0.72222 | 11.6667 | 0 | 7 | 30 | 42.3333 | 41.6667 | 54 | 12.3333 | 30 | 41.6667 | 0%
| 8 | 0 | G | RUN ELECTRIC LINE | C |  |  | Tri | 8 | 10 | 12 | 10 | 0.8165 | 0.66667 | 10 | 0 | 8 | 30 | 44 | 40 | 54 | 14 | 30 | 40 | 0%
| 9 | 1 | H | MOUNT UNIT | D | E |  | Tri | 4 | 5 | 12 | 7 | 1.7795 | 3.1667 | 7 | 0 | 9 | 37 | 37 | 44 | 44 | 0 | 37 | 44 | 0%
| 10 | 0 | I | INSTALL ELECTRIC MOTOR | H |  |  | Tri | 3 | 4 | 5 | 4 | 0.40825 | 0.16667 | 4 | 0 | 10 | 44 | 50 | 48 | 54 | 6 | 44 | 48 | 0%
| 11 | 1 | J | RUN SUCKER RODS | H |  |  | Tri | 4 | 8 | 18 | 10 | 2.9439 | 8.6667 | 10 | 0 | 11 | 44 | 44 | 54 | 54 | 0 | 44 | 54 | 0%
| 12 | 0 | K | TIE IN, TEST MOTOR | G | I |  | Tri | 1 | 1 | 4 | 2 | 0.70711 | 0.5 | 2 | 0 | 12 | 48 | 54 | 50 | 56 | 6 | 48 | 50 | 0%
| 13 | 1 | L | NIPPLE UP WELL HEAD | F | J |  | Tri | 1 | 1 | 4 | 2 | 0.70711 | 0.5 | 2 | 0 | 13 | 54 | 54 | 56 | 56 | 0 | 54 | 56 | 0%
| 14 | 1 | M | TEST PUMP | K | L |  | Tri | 1 | 4 | 10 | 5 | 1.8708 | 3.5 | 5 | 0 | 14 | 56 | 56 | 61 | 61 | 0 | 56 | 61 | 0%
| 15 | 0 | N | OPEN VALUES | K | L |  | Tri | 0.12 | 1 | 2 | 1.04 | 0.38401 | 0.14747 | 1.04 | 0 | 15 | 56 | 59.96 | 57.04 | 61 | 3.96 | 56 | 57.04 | 0%
| 16 | 1 | End | Activity End |  |  |  | Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 61 | 61 | 61 | 61 | 0 | 61 | 61 | 0%
16

## PumpRV_Network
Network PumpRV
Activity on Node Network
Sorted Activity Nodes |  |  |  |  | Sorted Precedence Arcs
[6 empty] | From | To | From | To | Critical
Index | Sort | Name | Level | Depth | Index | Index | Index | Name | Name | Arc
1 | 1 | Start | 0 | 0 | 1 | 1 | 2 | Start | A | 1
2 | 2 | A | 1 | 0 | 2 | 1 | 3 | Start | B | 1
3 | 3 | B | 1 | 1 | 3 | 1 | 4 | Start | C | 1
4 | 4 | C | 1 | 2 | 4 | 2 | 5 | A | D | 1
5 | 5 | D | 2 | 0 | 5 | 3 | 6 | B | E | 1
6 | 6 | E | 2 | 1 | 6 | 4 | 7 | C | F | 1
7 | 7 | F | 2 | 2 | 7 | 4 | 8 | C | G | 1
8 | 8 | G | 2 | 3 | 8 | 5 | 9 | D | H | 1
9 | 9 | H | 3 | 0 | 9 | 6 | 9 | E | H | 1
10 | 10 | I | 4 | 0 | 10 | 7 | 13 | F | L | 1
11 | 11 | J | 4 | 1 | 11 | 8 | 12 | G | K | 1
12 | 12 | K | 5 | 0 | 12 | 9 | 10 | H | I | 1
13 | 13 | L | 5 | 1 | 13 | 9 | 11 | H | J | 1
14 | 14 | M | 6 | 0 | 14 | 10 | 12 | I | K | 1
15 | 15 | N | 6 | 1 | 15 | 11 | 13 | J | L | 1
16 | 16 | End | 7 | 0 | 16 | 12 | 14 | K | M | 1
[5 empty] | 17 | 12 | 15 | K | N | 1
[5 empty] | 18 | 13 | 14 | L | M | 1
[5 empty] | 19 | 13 | 15 | L | N | 1
[5 empty] | 20 | 14 | 16 | M | End | 1
[5 empty] | 21 | 15 | 16 | N | End | 1

## PumpRV_Schedule
Schedule PumpRV
Search
Transfer Schedule
|  |  | Activities |  |  |  |  | Schedule Limits |  |  |  |  | Schedule Decisions |  |  |  | Gantt Chart
Bucket | 1 | Hours | [5 empty] | Early | Late | Early | Late |  | Activity | Sched. | Sched. | Perc. | Proj. Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72
|  |  | Index | Sort | Name | Description | Time | Start | Start | Finish | Finish | Slack | Delay | Start | Finish | Finished | Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completion Time |  |  | 1 | 1 | Start | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Due | 59 | Hours | 2 | 2 | A | POUR SLAB | 13 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 13 | 0% | POUR SLAB | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Max Delay | 2 | Hours | 3 | 3 | B | ORDER PUMP UNIT | 0.25 | 0 | 29.75 | 0.25 | 30 | 29.75 | 0 | 0 | 0.25 | 0% | ORDER PUMP UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay Unit Cost | 1 | /Hours | 4 | 4 | C | CUT PATH | 30 | 0 | 12.3333 | 30 | 42.3333 | 12.3333 | 0 | 0 | 30 | 0% | CUT PATH | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled | 61 | Hours | 5 | 5 | D | CURE SLAB | 24 | 13 | 13 | 37 | 37 | 0 | 0 | 13 | 37 | 0% | CURE SLAB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6 | 6 | E | DELIVER UNIT | 7 | 0.25 | 30 | 7.25 | 37 | 29.75 | 0 | 0.25 | 7.25 | 0% | DELIVER UNIT | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7 | 7 | F | RUN FLOW LINE | 11.6667 | 30 | 42.3333 | 41.6667 | 54 | 12.3333 | 0 | 30 | 41.6667 | 0% | RUN FLOW LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Costs |  |  | 8 | 8 | G | RUN ELECTRIC LINE | 10 | 30 | 44 | 40 | 54 | 14 | 0 | 30 | 40 | 0% | RUN ELECTRIC LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay | 2 |  | 9 | 9 | H | MOUNT UNIT | 7 | 37 | 37 | 44 | 44 | 0 | 0 | 37 | 44 | 0% | MOUNT UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10 | 10 | I | INSTALL ELECTRIC MOTOR | 4 | 44 | 50 | 48 | 54 | 6 | 0 | 44 | 48 | 0% | INSTALL ELECTRIC MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasibility |  |  | 11 | 11 | J | RUN SUCKER RODS | 10 | 44 | 44 | 54 | 54 | 0 | 0 | 44 | 54 | 0% | RUN SUCKER RODS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Late | 0 |  | 12 | 12 | K | TIE IN, TEST MOTOR | 2 | 48 | 54 | 50 | 56 | 6 | 0 | 48 | 50 | 0% | TIE IN, TEST MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule | 0 |  | 13 | 13 | L | NIPPLE UP WELL HEAD | 2 | 54 | 54 | 56 | 56 | 0 | 0 | 54 | 56 | 0% | NIPPLE UP WELL HEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasible | TRUE |  | 14 | 14 | M | TEST PUMP | 5 | 56 | 56 | 61 | 61 | 0 | 0 | 56 | 61 | 0% | TEST PUMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 15 | 15 | N | OPEN VALUES | 1.04 | 56 | 59.96 | 57.04 | 61 | 3.96 | 0 | 56 | 57.04 | 0% | OPEN VALUES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 16 | 16 | End | Activity End | 0 | 61 | 61 | 61 | 61 | 0 | 0 | 61 | 61 | 0% | Activity End | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PumpBeta
Project PumpBeta | [15 empty] | Times(Proj. Hours)
[16 empty] | Due | 59
| Solve |  | Simulate | [12 empty] | Critical | 59.5481
[16 empty] | Var. | 16.4688
| Change |  | Gantt | [12 empty] | SD. | 4.0582
[16 empty] | On Time Prob. | 0.44629
| Critical |  | Graph | [12 empty] | Slack | 0
[9 empty] | Mean | [6 empty] | Late | 0.54805
| Update |  | Schedule | [5 empty] | 40% | [6 empty] | Current | 0
|  | Activity Data | [5 empty] | Activity Time Estimates | [10 empty] | Schedule Limits |  |  |  |  | Schedule Decisions
[16 empty] | Time | Activity |  | Early | Late | Early | Late |  | Sched. | Sched. | Perc.
|  | Critical | Name | Description | Predecessors |  | Color | Dist. | Alpha | Beta | Min. | Max. | Mean | S.D. | Var. | Hours | Delay | Sort | Start | Start | Finish | Finish | Slack | Start | Finish | Finished
| 1 | 1 | Start | Activity Start |  |  |  | Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| 2 | 1 | A | POUR SLAB |  |  |  | Beta | 2 | 5 | 9 | 19 | 11.8571 | 1.5972 | 2.551 | 11.8571 | 0 | 2 | 0 | 0 | 11.8571 | 11.8571 | 0 | 0 | 11.8571 | 0%
| 3 | 0 | B | ORDER PUMP UNIT |  |  |  | Beta | 2 | 2 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0 | 3 | 0 | 28.6071 | 0.25 | 28.8571 | 28.6071 | 0 | 0.25 | 0%
| 4 | 0 | C | CUT PATH |  |  |  | Beta | 2 | 2 | 20 | 40 | 30 | 4.4721 | 20 | 30 | 0 | 4 | 0 | 11.6147 | 30 | 41.6147 | 11.6147 | 0 | 30 | 0%
| 5 | 1 | D | CURE SLAB | A |  |  | Beta | 2 | 2 | 24 | 24 | 24 | 0 | 0 | 24 | 0 | 5 | 11.8571 | 11.8571 | 35.8571 | 35.8571 | 0 | 11.8571 | 35.8571 | 0%
| 6 | 0 | E | DELIVER UNIT | B |  |  | Beta | 2 | 1 | 3 | 9 | 7 | 1.4142 | 2 | 7 | 0 | 6 | 0.25 | 28.8571 | 7.25 | 35.8571 | 28.6071 | 0.25 | 7.25 | 0%
| 7 | 0 | F | RUN FLOW LINE | C |  |  | Beta | 2 | 4 | 10 | 14 | 11.3333 | 0.7127 | 0.50794 | 11.3333 | 0 | 7 | 30 | 41.6147 | 41.3333 | 52.9481 | 11.6147 | 30 | 41.3333 | 0%
| 8 | 0 | G | RUN ELECTRIC LINE | C |  |  | Beta | 2 | 2 | 8 | 12 | 10 | 0.89443 | 0.8 | 10 | 0 | 8 | 30 | 42.9481 | 40 | 52.9481 | 12.9481 | 30 | 40 | 0%
| 9 | 1 | H | MOUNT UNIT | D | E |  | Beta | 2 | 2 | 4 | 12 | 8 | 1.7889 | 3.2 | 8 | 0 | 9 | 35.8571 | 35.8571 | 43.8571 | 43.8571 | 0 | 35.8571 | 43.8571 | 0%
| 10 | 0 | I | INSTALL ELECTRIC MOTOR | H |  |  | Beta | 2 | 2 | 3 | 5 | 4 | 0.44721 | 0.2 | 4 | 0 | 10 | 43.8571 | 48.9481 | 47.8571 | 52.9481 | 5.0909 | 43.8571 | 47.8571 | 0%
| 11 | 1 | J | RUN SUCKER RODS | H |  |  | Beta | 2 | 3.5 | 4 | 18 | 9.0909 | 2.6415 | 6.9777 | 9.0909 | 0 | 11 | 43.8571 | 43.8571 | 52.9481 | 52.9481 | 0 | 43.8571 | 52.9481 | 0%
| 12 | 0 | K | TIE IN, TEST MOTOR | G | I |  | Beta | 1 | 2 | 1 | 4 | 2 | 0.70711 | 0.5 | 2 | 0 | 12 | 47.8571 | 52.9481 | 49.8571 | 54.9481 | 5.0909 | 47.8571 | 49.8571 | 0%
| 13 | 1 | L | NIPPLE UP WELL HEAD | F | J |  | Beta | 1 | 2 | 1 | 4 | 2 | 0.70711 | 0.5 | 2 | 0 | 13 | 52.9481 | 52.9481 | 54.9481 | 54.9481 | 0 | 52.9481 | 54.9481 | 0%
| 14 | 1 | M | TEST PUMP | K | L |  | Beta | 2 | 3 | 1 | 10 | 4.6 | 1.8 | 3.24 | 4.6 | 0 | 14 | 54.9481 | 54.9481 | 59.5481 | 59.5481 | 0 | 54.9481 | 59.5481 | 0%
| 15 | 0 | N | OPEN VALUES | K | L |  | Beta | 2 | 2.1364 | 0.12 | 2 | 1.029 | 0.41454 | 0.17184 | 1.029 | 0 | 15 | 54.9481 | 58.519 | 55.9771 | 59.5481 | 3.571 | 54.9481 | 55.9771 | 0%
| 16 | 1 | End | Activity End |  |  |  | Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 59.5481 | 59.5481 | 59.5481 | 59.5481 | 0 | 59.5481 | 59.5481 | 0%
16
Estimate
Percentile

## PumpBeta_Network
Network PumpBeta
Activity on Node Network
Sorted Activity Nodes |  |  |  |  | Sorted Precedence Arcs
[6 empty] | From | To | From | To | Critical
Index | Sort | Name | Level | Depth | Index | Index | Index | Name | Name | Arc
1 | 1 | Start | 0 | 0 | 1 | 1 | 2 | Start | A | 1
2 | 2 | A | 1 | 0 | 2 | 1 | 3 | Start | B | 1
3 | 3 | B | 1 | 1 | 3 | 1 | 4 | Start | C | 1
4 | 4 | C | 1 | 2 | 4 | 2 | 5 | A | D | 1
5 | 5 | D | 2 | 0 | 5 | 3 | 6 | B | E | 1
6 | 6 | E | 2 | 1 | 6 | 4 | 7 | C | F | 1
7 | 7 | F | 2 | 2 | 7 | 4 | 8 | C | G | 1
8 | 8 | G | 2 | 3 | 8 | 5 | 9 | D | H | 1
9 | 9 | H | 3 | 0 | 9 | 6 | 9 | E | H | 1
10 | 10 | I | 4 | 0 | 10 | 7 | 13 | F | L | 1
11 | 11 | J | 4 | 1 | 11 | 8 | 12 | G | K | 1
12 | 12 | K | 5 | 0 | 12 | 9 | 10 | H | I | 1
13 | 13 | L | 5 | 1 | 13 | 9 | 11 | H | J | 1
14 | 14 | M | 6 | 0 | 14 | 10 | 12 | I | K | 1
15 | 15 | N | 6 | 1 | 15 | 11 | 13 | J | L | 1
16 | 16 | End | 7 | 0 | 16 | 12 | 14 | K | M | 1
[5 empty] | 17 | 12 | 15 | K | N | 1
[5 empty] | 18 | 13 | 14 | L | M | 1
[5 empty] | 19 | 13 | 15 | L | N | 1
[5 empty] | 20 | 14 | 16 | M | End | 1
[5 empty] | 21 | 15 | 16 | N | End | 1

## PumpCal
Project PumpCal |  |  |  | Start and Due Dates | [11 empty] | Times(Proj. Hours) | [10 empty] | Calendar |  |  | Gantt Parmeters
|  |  |  | 2005-02-15 | Project Start | [10 empty] | Due | 60 | [8 empty] | Start | 2005-02-15 |  | Bucket | 1
| Solve |  |  | 2005-02-20 | Project Due | [10 empty] | Critical | 57 | [8 empty] | Due | 2005-02-20 |  | Start | 0
|  |  |  | 0 | Start Hours | [10 empty] | Var. | 12.5 | [8 empty] | Critical | 2005-02-19 |  | Horizon | 59
| Change |  | Gantt | [12 empty] | SD. | 3.5355 | [8 empty] | Slack(Days) | 1 |  | Extra | 10
[16 empty] | On Time Prob. | 0.80193 | [8 empty] | Late(Days) | 0
| Critical |  | Graph | [12 empty] | Slack | 3 | [8 empty] | Current | 2005-02-15
[16 empty] | Late | 0
| Update |  | Schedule | [12 empty] | Current | 0
|  | Activity Data | [6 empty] | Resources | Activity Time Estimates | [8 empty] | Schedule Limits |  |  |  |  | Schedule Decisions | [5 empty] | Gantt Chart | 2005-02-15 |  |  |  |  | 2005-02-15 |  |  |  |  | 2005-02-15 |  |  |  |  | 2005-02-16 |  |  |  |  | 2005-02-16 |  |  |  |  | 2005-02-17 |  |  |  |  | 2005-02-17 |  |  |  |  | 2005-02-18 |  |  |  |  | 2005-02-18 |  |  |  |  | 2005-02-18 |  |  |  |  | 2005-02-19 |  |  |  |  | 2005-02-19 |  |  |  |  | 2005-02-20 |  |  |  |  | 2005-02-20
[11 empty] | Most |  |  |  |  | Time | Activity |  | Early | Late | Early | Late |  | Sched. | Sched. | Start | Finish | Perc. |  | Proj. Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69
|  | Critical | Name | Description | Predecessors |  |  | Color | Res. 1 | Min. | Likely | Max. | Mean | S.D. | Var. | Hours | Delay | Sort | Start | Start | Finish | Finish | Slack | Start | Finish | Date | Date | Finished |  | Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 1 | Start | Activity Start |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 2005-02-15 | 2005-02-15 | 0% |  | Activity Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 1 | A | POUR SLAB |  |  |  |  | 4 | 9 | 11 | 19 | 12 | 1.6667 | 2.7778 | 12 | 0 | 2 | 0 | 3 | 12 | 15 | 3 | 0 | 12 | 2005-02-15 | 2005-02-16 | 0% |  | POUR SLAB | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | B | ORDER PUMP UNIT |  |  |  |  | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0 | 3 | 0 | 30.75 | 0.25 | 31 | 30.75 | 0 | 0.25 | 2005-02-15 | 2005-02-15 | 0% |  | ORDER PUMP UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | C | CUT PATH |  |  |  |  | 6 | 20 | 30 | 40 | 30 | 3.3333 | 11.1111 | 30 | 0 | 4 | 0 | 12.6667 | 30 | 42.6667 | 12.6667 | 0 | 30 | 2005-02-15 | 2005-02-17 | 0% |  | CUT PATH | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | 1 | D | CURE SLAB | A |  |  |  | 0 | 24 | 24 | 24 | 24 | 0 | 0 | 24 | 0 | 5 | 12 | 15 | 36 | 39 | 3 | 12 | 36 | 2005-02-16 | 2005-02-18 | 0% |  | CURE SLAB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 0 | E | DELIVER UNIT | B |  |  |  | 0 | 3 | 9 | 9 | 8 | 1 | 1 | 8 | 0 | 6 | 0.25 | 31 | 8.25 | 39 | 30.75 | 0.25 | 8.25 | 2005-02-15 | 2005-02-15 | 0% |  | DELIVER UNIT | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | F | RUN FLOW LINE | C |  |  |  | 6 | 10 | 11 | 14 | 11.3333 | 0.66667 | 0.44444 | 11.3333 | 0 | 7 | 30 | 42.6667 | 41.3333 | 54 | 12.6667 | 30 | 41.3333 | 2005-02-17 | 2005-02-18 | 0% |  | RUN FLOW LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | 0 | G | RUN ELECTRIC LINE | C |  |  |  | 3 | 8 | 10 | 12 | 10 | 0.66667 | 0.44444 | 10 | 0 | 8 | 30 | 44 | 40 | 54 | 14 | 30 | 40 | 2005-02-17 | 2005-02-18 | 0% |  | RUN ELECTRIC LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | 1 | H | MOUNT UNIT | D | E |  |  | 3 | 4 | 5 | 12 | 6 | 1.3333 | 1.7778 | 6 | 0 | 9 | 36 | 39 | 42 | 45 | 3 | 36 | 42 | 2005-02-18 | 2005-02-18 | 0% |  | MOUNT UNIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | 0 | I | INSTALL ELECTRIC MOTOR | H |  |  |  | 2 | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 4 | 0 | 10 | 42 | 50 | 46 | 54 | 8 | 42 | 46 | 2005-02-18 | 2005-02-18 | 0% |  | INSTALL ELECTRIC MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | 1 | J | RUN SUCKER RODS | H |  |  |  | 3 | 4 | 8 | 18 | 9 | 2.3333 | 5.4444 | 9 | 0 | 11 | 42 | 45 | 51 | 54 | 3 | 42 | 51 | 2005-02-18 | 2005-02-19 | 0% |  | RUN SUCKER RODS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | 0 | K | TIE IN, TEST MOTOR | G | I |  |  | 1 | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | 0 | 12 | 46 | 54 | 47.5 | 55.5 | 8 | 46 | 47.5 | 2005-02-18 | 2005-02-18 | 0% |  | TIE IN, TEST MOTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | 1 | L | NIPPLE UP WELL HEAD | F | J |  |  | 2 | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | 0 | 13 | 51 | 54 | 52.5 | 55.5 | 3 | 51 | 52.5 | 2005-02-19 | 2005-02-19 | 0% |  | NIPPLE UP WELL HEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14 | 1 | M | TEST PUMP | K | L |  |  | 2 | 1 | 4 | 10 | 4.5 | 1.5 | 2.25 | 4.5 | 0 | 14 | 52.5 | 55.5 | 57 | 60 | 3 | 52.5 | 57 | 2005-02-19 | 2005-02-19 | 0% |  | TEST PUMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 | 0 | N | OPEN VALUES | K | L |  |  | 1 | 0.12 | 1 | 2 | 1.02 | 0.31333 | 0.098178 | 1.02 | 0 | 15 | 52.5 | 58.98 | 53.52 | 60 | 6.48 | 52.5 | 53.52 | 2005-02-19 | 2005-02-19 | 0% |  | OPEN VALUES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16 | 1 | End | Activity End |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 57 | 60 | 57 | 60 | 3 | 57 | 57 | 2005-02-19 | 2005-02-19 | 0% |  | Activity End | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16
Formulas:
Calendar = LOOKUP([Sched.]+PumpCal_ProjStMeas,PumpCal_CalProjInt,PumpCal_CalDate)
Start = LOOKUP([Sched.]+PumpCal_ProjStMeas,PumpCal_CalProjInt,PumpCal_CalDate)

## PumpCal_Network
Network PumpCal
Activity on Node Network
Sorted Activity Nodes |  |  |  |  | Sorted Precedence Arcs
[6 empty] | From | To | From | To | Critical
Index | Sort | Name | Level | Depth | Index | Index | Index | Name | Name | Arc
1 | 1 | Start | 0 | 0 | 1 | 1 | 2 | Start | A | 1
2 | 2 | A | 1 | 0 | 2 | 1 | 3 | Start | B | 1
3 | 3 | B | 1 | 1 | 3 | 1 | 4 | Start | C | 1
4 | 4 | C | 1 | 2 | 4 | 2 | 5 | A | D | 1
5 | 5 | D | 2 | 0 | 5 | 3 | 6 | B | E | 1
6 | 6 | E | 2 | 1 | 6 | 4 | 7 | C | F | 1
7 | 7 | F | 2 | 2 | 7 | 4 | 8 | C | G | 1
8 | 8 | G | 2 | 3 | 8 | 5 | 9 | D | H | 1
9 | 9 | H | 3 | 0 | 9 | 6 | 9 | E | H | 1
10 | 10 | I | 4 | 0 | 10 | 7 | 13 | F | L | 1
11 | 11 | J | 4 | 1 | 11 | 8 | 12 | G | K | 1
12 | 12 | K | 5 | 0 | 12 | 9 | 10 | H | I | 1
13 | 13 | L | 5 | 1 | 13 | 9 | 11 | H | J | 1
14 | 14 | M | 6 | 0 | 14 | 10 | 12 | I | K | 1
15 | 15 | N | 6 | 1 | 15 | 11 | 13 | J | L | 1
16 | 16 | End | 7 | 0 | 16 | 12 | 14 | K | M | 1
[5 empty] | 17 | 12 | 15 | K | N | 1
[5 empty] | 18 | 13 | 14 | L | M | 1
[5 empty] | 19 | 13 | 15 | L | N | 1
[5 empty] | 20 | 14 | 16 | M | End | 1
[5 empty] | 21 | 15 | 16 | N | End | 1

## PumpCal_Calendar
Calendar PumpCal
Proj. Hours
Calendar Parameters |  |  | Date | /Cal. Day | Proj. Hours
Cal. Start | 2005-02-15 | 1 | 2005-02-15 | 12 | 0
Cal. End | 2005-09-03 | 2 | 2005-02-16 | 12 | 12
Cal. Interval | Day | 3 | 2005-02-17 | 12 | 24
Cal. Length | 200 | 4 | 2005-02-18 | 12 | 36
Proj. Hours/Cal. Day | 12 | 5 | 2005-02-19 | 12 | 48
Max. Proj. Date | 2388 | 6 | 2005-02-20 | 12 | 60
|  | 7 | 2005-02-21 | 12 | 72
|  | 8 | 2005-02-22 | 12 | 84
|  | 9 | 2005-02-23 | 12 | 96
|  | 10 | 2005-02-24 | 12 | 108
|  | 11 | 2005-02-25 | 12 | 120
|  | 12 | 2005-02-26 | 12 | 132
|  | 13 | 2005-02-27 | 12 | 144
|  | 14 | 2005-02-28 | 12 | 156
|  | 15 | 2005-03-01 | 12 | 168
|  | 16 | 2005-03-02 | 12 | 180
|  | 17 | 2005-03-03 | 12 | 192
|  | 18 | 2005-03-04 | 12 | 204
|  | 19 | 2005-03-05 | 12 | 216
|  | 20 | 2005-03-06 | 12 | 228
|  | 21 | 2005-03-07 | 12 | 240
|  | 22 | 2005-03-08 | 12 | 252
|  | 23 | 2005-03-09 | 12 | 264
|  | 24 | 2005-03-10 | 12 | 276
|  | 25 | 2005-03-11 | 12 | 288
|  | 26 | 2005-03-12 | 12 | 300
|  | 27 | 2005-03-13 | 12 | 312
|  | 28 | 2005-03-14 | 12 | 324
|  | 29 | 2005-03-15 | 12 | 336
|  | 30 | 2005-03-16 | 12 | 348
|  | 31 | 2005-03-17 | 12 | 360
|  | 32 | 2005-03-18 | 12 | 372
|  | 33 | 2005-03-19 | 12 | 384
|  | 34 | 2005-03-20 | 12 | 396
|  | 35 | 2005-03-21 | 12 | 408
|  | 36 | 2005-03-22 | 12 | 420
|  | 37 | 2005-03-23 | 12 | 432
|  | 38 | 2005-03-24 | 12 | 444
|  | 39 | 2005-03-25 | 12 | 456
|  | 40 | 2005-03-26 | 12 | 468
|  | 41 | 2005-03-27 | 12 | 480
|  | 42 | 2005-03-28 | 12 | 492
|  | 43 | 2005-03-29 | 12 | 504
|  | 44 | 2005-03-30 | 12 | 516
|  | 45 | 2005-03-31 | 12 | 528
|  | 46 | 2005-04-01 | 12 | 540
|  | 47 | 2005-04-02 | 12 | 552
|  | 48 | 2005-04-03 | 12 | 564
|  | 49 | 2005-04-04 | 12 | 576
|  | 50 | 2005-04-05 | 12 | 588
|  | 51 | 2005-04-06 | 12 | 600
|  | 52 | 2005-04-07 | 12 | 612
|  | 53 | 2005-04-08 | 12 | 624
|  | 54 | 2005-04-09 | 12 | 636
|  | 55 | 2005-04-10 | 12 | 648
|  | 56 | 2005-04-11 | 12 | 660
|  | 57 | 2005-04-12 | 12 | 672
|  | 58 | 2005-04-13 | 12 | 684
|  | 59 | 2005-04-14 | 12 | 696
|  | 60 | 2005-04-15 | 12 | 708
|  | 61 | 2005-04-16 | 12 | 720
|  | 62 | 2005-04-17 | 12 | 732
|  | 63 | 2005-04-18 | 12 | 744
|  | 64 | 2005-04-19 | 12 | 756
|  | 65 | 2005-04-20 | 12 | 768
|  | 66 | 2005-04-21 | 12 | 780
|  | 67 | 2005-04-22 | 12 | 792
|  | 68 | 2005-04-23 | 12 | 804
|  | 69 | 2005-04-24 | 12 | 816
|  | 70 | 2005-04-25 | 12 | 828
|  | 71 | 2005-04-26 | 12 | 840
|  | 72 | 2005-04-27 | 12 | 852
|  | 73 | 2005-04-28 | 12 | 864
|  | 74 | 2005-04-29 | 12 | 876
|  | 75 | 2005-04-30 | 12 | 888
|  | 76 | 2005-05-01 | 12 | 900
|  | 77 | 2005-05-02 | 12 | 912
|  | 78 | 2005-05-03 | 12 | 924
|  | 79 | 2005-05-04 | 12 | 936
|  | 80 | 2005-05-05 | 12 | 948
|  | 81 | 2005-05-06 | 12 | 960
|  | 82 | 2005-05-07 | 12 | 972
|  | 83 | 2005-05-08 | 12 | 984
|  | 84 | 2005-05-09 | 12 | 996
|  | 85 | 2005-05-10 | 12 | 1008
|  | 86 | 2005-05-11 | 12 | 1020
|  | 87 | 2005-05-12 | 12 | 1032
|  | 88 | 2005-05-13 | 12 | 1044
|  | 89 | 2005-05-14 | 12 | 1056
|  | 90 | 2005-05-15 | 12 | 1068
|  | 91 | 2005-05-16 | 12 | 1080
|  | 92 | 2005-05-17 | 12 | 1092
|  | 93 | 2005-05-18 | 12 | 1104
|  | 94 | 2005-05-19 | 12 | 1116
|  | 95 | 2005-05-20 | 12 | 1128
|  | 96 | 2005-05-21 | 12 | 1140
|  | 97 | 2005-05-22 | 12 | 1152
|  | 98 | 2005-05-23 | 12 | 1164
|  | 99 | 2005-05-24 | 12 | 1176
|  | 100 | 2005-05-25 | 12 | 1188
|  | 101 | 2005-05-26 | 12 | 1200
|  | 102 | 2005-05-27 | 12 | 1212
|  | 103 | 2005-05-28 | 12 | 1224
|  | 104 | 2005-05-29 | 12 | 1236
|  | 105 | 2005-05-30 | 12 | 1248
|  | 106 | 2005-05-31 | 12 | 1260
|  | 107 | 2005-06-01 | 12 | 1272
|  | 108 | 2005-06-02 | 12 | 1284
|  | 109 | 2005-06-03 | 12 | 1296
|  | 110 | 2005-06-04 | 12 | 1308
|  | 111 | 2005-06-05 | 12 | 1320
|  | 112 | 2005-06-06 | 12 | 1332
|  | 113 | 2005-06-07 | 12 | 1344
|  | 114 | 2005-06-08 | 12 | 1356
|  | 115 | 2005-06-09 | 12 | 1368
|  | 116 | 2005-06-10 | 12 | 1380
|  | 117 | 2005-06-11 | 12 | 1392
|  | 118 | 2005-06-12 | 12 | 1404
|  | 119 | 2005-06-13 | 12 | 1416
|  | 120 | 2005-06-14 | 12 | 1428
|  | 121 | 2005-06-15 | 12 | 1440
|  | 122 | 2005-06-16 | 12 | 1452
|  | 123 | 2005-06-17 | 12 | 1464
|  | 124 | 2005-06-18 | 12 | 1476
|  | 125 | 2005-06-19 | 12 | 1488
|  | 126 | 2005-06-20 | 12 | 1500
|  | 127 | 2005-06-21 | 12 | 1512
|  | 128 | 2005-06-22 | 12 | 1524
|  | 129 | 2005-06-23 | 12 | 1536
|  | 130 | 2005-06-24 | 12 | 1548
|  | 131 | 2005-06-25 | 12 | 1560
|  | 132 | 2005-06-26 | 12 | 1572
|  | 133 | 2005-06-27 | 12 | 1584
|  | 134 | 2005-06-28 | 12 | 1596
|  | 135 | 2005-06-29 | 12 | 1608
|  | 136 | 2005-06-30 | 12 | 1620
|  | 137 | 2005-07-01 | 12 | 1632
|  | 138 | 2005-07-02 | 12 | 1644
|  | 139 | 2005-07-03 | 12 | 1656
|  | 140 | 2005-07-04 | 12 | 1668
|  | 141 | 2005-07-05 | 12 | 1680
|  | 142 | 2005-07-06 | 12 | 1692
|  | 143 | 2005-07-07 | 12 | 1704
|  | 144 | 2005-07-08 | 12 | 1716
|  | 145 | 2005-07-09 | 12 | 1728
|  | 146 | 2005-07-10 | 12 | 1740
|  | 147 | 2005-07-11 | 12 | 1752
|  | 148 | 2005-07-12 | 12 | 1764
|  | 149 | 2005-07-13 | 12 | 1776
|  | 150 | 2005-07-14 | 12 | 1788
|  | 151 | 2005-07-15 | 12 | 1800
|  | 152 | 2005-07-16 | 12 | 1812
|  | 153 | 2005-07-17 | 12 | 1824
|  | 154 | 2005-07-18 | 12 | 1836
|  | 155 | 2005-07-19 | 12 | 1848
|  | 156 | 2005-07-20 | 12 | 1860
|  | 157 | 2005-07-21 | 12 | 1872
|  | 158 | 2005-07-22 | 12 | 1884
|  | 159 | 2005-07-23 | 12 | 1896
|  | 160 | 2005-07-24 | 12 | 1908
|  | 161 | 2005-07-25 | 12 | 1920
|  | 162 | 2005-07-26 | 12 | 1932
|  | 163 | 2005-07-27 | 12 | 1944
|  | 164 | 2005-07-28 | 12 | 1956
|  | 165 | 2005-07-29 | 12 | 1968
|  | 166 | 2005-07-30 | 12 | 1980
|  | 167 | 2005-07-31 | 12 | 1992
|  | 168 | 2005-08-01 | 12 | 2004
|  | 169 | 2005-08-02 | 12 | 2016
|  | 170 | 2005-08-03 | 12 | 2028
|  | 171 | 2005-08-04 | 12 | 2040
|  | 172 | 2005-08-05 | 12 | 2052
|  | 173 | 2005-08-06 | 12 | 2064
|  | 174 | 2005-08-07 | 12 | 2076
|  | 175 | 2005-08-08 | 12 | 2088
|  | 176 | 2005-08-09 | 12 | 2100
|  | 177 | 2005-08-10 | 12 | 2112
|  | 178 | 2005-08-11 | 12 | 2124
|  | 179 | 2005-08-12 | 12 | 2136
|  | 180 | 2005-08-13 | 12 | 2148
|  | 181 | 2005-08-14 | 12 | 2160
|  | 182 | 2005-08-15 | 12 | 2172
|  | 183 | 2005-08-16 | 12 | 2184
|  | 184 | 2005-08-17 | 12 | 2196
|  | 185 | 2005-08-18 | 12 | 2208
|  | 186 | 2005-08-19 | 12 | 2220
|  | 187 | 2005-08-20 | 12 | 2232
|  | 188 | 2005-08-21 | 12 | 2244
|  | 189 | 2005-08-22 | 12 | 2256
|  | 190 | 2005-08-23 | 12 | 2268
|  | 191 | 2005-08-24 | 12 | 2280
|  | 192 | 2005-08-25 | 12 | 2292
|  | 193 | 2005-08-26 | 12 | 2304
|  | 194 | 2005-08-27 | 12 | 2316
|  | 195 | 2005-08-28 | 12 | 2328
|  | 196 | 2005-08-29 | 12 | 2340
|  | 197 | 2005-08-30 | 12 | 2352
|  | 198 | 2005-08-31 | 12 | 2364
|  | 199 | 2005-09-01 | 12 | 2376
|  | 200 | 2005-09-02 | 12 | 2388
|  | 201 | *** | 12 | 2400
|  | 202 | 2005-09-03 | 12 | ***