## House
Project Management
| Solve |  | Show Critical |  |  | Schedule
| Change |  | Graph | [25 empty] | Activity on Node Network
[29 empty] | Sorted Activity Nodes | [10 empty] | Sorted Precedence Arcs
|  |  |  | Activity Data |  |  | Activity Time Estimates | [10 empty] | Cash Flows |  |  |  |  | Schedule |  |  |  | Difference | 0.001 |  |  |  |  | Early | Late | Early | Late | Critical |  |  |  | From | To | From | To | Critical
[8 empty] | Most |  |  |  |  | Time |  |  |  |  | Initial | Uniform | Final | Resources |  | Early | Late | Early | Late |  | Near | Index | Sort | Name | Time | Start | Start | Finish | Finish | Node | Level | Depth | Index | Index | Index | Name | Name | Arc
|  |  |  | Critical | Name | Description | Min. | Likely | Max. | Mean | S.D. | Var. | DAYS | Predecessors |  |  |  | C.F. | C.F. | C.F. | Res. 1 | Sort | Start | Start | Finish | Finish | Slack | Critical | 1 | 1 | Start | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2 | Start | A | 1
Critical Path |  |  | 1 | 1 | A | OBTAIN BLDG PERMIT | 0.5 | 1 | 2 | 1.0833 | 0.25 | 0.0625 | 1.0833 |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1.0833 | 1.0833 | 0 | 1 | 2 | 2 | A | 1.0833 | 0 | 0 | 1.0833 | 1.0833 | 1 | 1 | 0 | 2 | 2 | 3 | A | B | 1
Exp. Time | 50.75 | DAYS | 2 | 1 | B | CLEAR LOT & GRADE | 1.5 | 2 | 4 | 2.25 | 0.41667 | 0.17361 | 2.25 | A |  |  |  | 0 | 0 | 0 | 0 | 3 | 1.0833 | 1.0833 | 3.3333 | 3.3333 | 0 | 1 | 3 | 3 | B | 2.25 | 1.0833 | 1.0833 | 3.3333 | 3.3333 | 1 | 2 | 0 | 3 | 3 | 4 | B | C | 1
Var. Time | 4.2708 |  | 3 | 1 | C | PLACE FORMS & RODS | 1.5 | 2 | 4 | 2.25 | 0.41667 | 0.17361 | 2.25 | B |  |  |  | 0 | 0 | 0 | 0 | 4 | 3.3333 | 3.3333 | 5.5833 | 5.5833 | 0 | 1 | 4 | 4 | C | 2.25 | 3.3333 | 3.3333 | 5.5833 | 5.5833 | 1 | 3 | 0 | 4 | 4 | 5 | C | D | 1
SD. Time | 2.0666 | DAYS | 4 | 1 | D | POUR SLAB | 1 | 1 | 1 | 1 | 0 | 0 | 1 | C |  |  |  | 0 | 0 | 0 | 0 | 5 | 5.5833 | 5.5833 | 6.5833 | 6.5833 | 0 | 1 | 5 | 5 | D | 1 | 5.5833 | 5.5833 | 6.5833 | 6.5833 | 1 | 4 | 0 | 5 | 5 | 6 | D | E | 1
|  |  | 5 | 1 | E | ERECT WOODEN FRME | 4 | 5 | 8 | 5.3333 | 0.66667 | 0.44444 | 5.3333 | D |  |  |  | 0 | 0 | 0 | 0 | 6 | 6.5833 | 6.5833 | 11.9167 | 11.9167 | 0 | 1 | 6 | 6 | E | 5.3333 | 6.5833 | 6.5833 | 11.9167 | 11.9167 | 1 | 5 | 0 | 6 | 6 | 7 | E | F | 0
Due | 50.75 | DAYS | 6 | 0 | F | FASTEN SHEATH | 1.5 | 2 | 3 | 2.0833 | 0.25 | 0.0625 | 2.0833 | E |  |  |  | 0 | 0 | 0 | 0 | 7 | 11.9167 | 13.0833 | 14 | 15.1667 | 1.1667 | 0 | 7 | 7 | F | 2.0833 | 11.9167 | 13.0833 | 14 | 15.1667 | 0 | 6 | 0 | 7 | 6 | 8 | E | G | 0
Probability | 0.5 |  | 7 | 0 | G | INSTALL RUF PLUMB | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25 | 3.1667 | E |  |  |  | 0 | 0 | 0 | 0 | 8 | 11.9167 | 12 | 15.0833 | 15.1667 | 0.083333 | 0 | 8 | 8 | G | 3.1667 | 11.9167 | 12 | 15.0833 | 15.1667 | 0 | 6 | 1 | 8 | 6 | 9 | E | H | 0
|  |  | 8 | 0 | H | INSTALL RUF WIRING | 2 | 2 | 4 | 2.3333 | 0.33333 | 0.11111 | 2.3333 | E |  |  |  | 0 | 0 | 0 | 0 | 9 | 11.9167 | 12.8333 | 14.25 | 15.1667 | 0.91667 | 0 | 9 | 9 | H | 2.3333 | 11.9167 | 12.8333 | 14.25 | 15.1667 | 0 | 6 | 2 | 9 | 6 | 10 | E | I | 1
|  |  | 9 | 1 | I | INSTALL HVAC DUCTS | 2.5 | 3 | 5 | 3.25 | 0.41667 | 0.17361 | 3.25 | E |  |  |  | 0 | 0 | 0 | 0 | 10 | 11.9167 | 11.9167 | 15.1667 | 15.1667 | 0 | 1 | 10 | 10 | I | 3.25 | 11.9167 | 11.9167 | 15.1667 | 15.1667 | 1 | 6 | 3 | 10 | 6 | 11 | E | J | 0
|  |  | 10 | 0 | J | SHINGLE ROOF | 2 | 2 | 3 | 2.1667 | 0.16667 | 0.027778 | 2.1667 | E |  |  |  | 0 | 0 | 0 | 0 | 11 | 11.9167 | 43.0833 | 14.0833 | 45.25 | 31.1667 | 0 | 11 | 11 | J | 2.1667 | 11.9167 | 43.0833 | 14.0833 | 45.25 | 0 | 6 | 4 | 11 | 6 | 12 | E | O | 0
|  |  | 11 | 0 | K | COMPLETE EXT TRIM | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25 | 3.1667 | F |  |  |  | 0 | 0 | 0 | 0 | 13 | 14 | 34.5833 | 17.1667 | 37.75 | 20.5833 | 0 | 12 | 16 | O | 5.3333 | 11.9167 | 14.4167 | 17.25 | 19.75 | 0 | 6 | 5 | 12 | 7 | 13 | F | K | 0
|  |  | 12 | 1 | L | INSULATE WALLS | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | F | G | H | I | 0 | 0 | 0 | 0 | 14 | 15.1667 | 15.1667 | 16.3333 | 16.3333 | 0 | 1 | 13 | 12 | K | 3.1667 | 14 | 34.5833 | 17.1667 | 37.75 | 0 | 7 | 0 | 13 | 7 | 14 | F | L | 0
|  |  | 13 | 0 | M | LAY BRICKWORK | 4.5 | 5 | 7 | 5.25 | 0.41667 | 0.17361 | 5.25 | K |  |  |  | 0 | 0 | 0 | 0 | 16 | 17.1667 | 37.75 | 22.4167 | 43 | 20.5833 | 0 | 14 | 13 | L | 1.1667 | 15.1667 | 15.1667 | 16.3333 | 16.3333 | 1 | 7 | 1 | 14 | 8 | 14 | G | L | 0
|  |  | 14 | 1 | N | SHEETROCK PLASTER | 2.5 | 3 | 6 | 3.4167 | 0.58333 | 0.34028 | 3.4167 | L |  |  |  | 0 | 0 | 0 | 0 | 17 | 16.3333 | 16.3333 | 19.75 | 19.75 | 0 | 1 | 15 | 24 | W | 2.1667 | 14.0833 | 45.25 | 16.25 | 47.4167 | 0 | 7 | 2 | 15 | 8 | 32 | G | Y | 0
|  |  | 15 | 0 | O | RUF CARPENTRY | 4 | 5 | 8 | 5.3333 | 0.66667 | 0.44444 | 5.3333 | E |  |  |  | 0 | 0 | 0 | 0 | 12 | 11.9167 | 14.4167 | 17.25 | 19.75 | 2.5 | 0 | 16 | 14 | M | 5.25 | 17.1667 | 37.75 | 22.4167 | 43 | 0 | 8 | 0 | 16 | 9 | 14 | H | L | 0
|  |  | 16 | 0 | P | INSTALL TUB & SHOWER | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | N | O |  |  | 0 | 0 | 0 | 0 | 19 | 19.75 | 31.1667 | 20.9167 | 32.3333 | 11.4167 | 0 | 17 | 15 | N | 3.4167 | 16.3333 | 16.3333 | 19.75 | 19.75 | 1 | 8 | 1 | 17 | 9 | 33 | H | Z | 0
|  |  | 17 | 1 | Q | FINISH CARPENTRY | 8 | 10 | 16 | 10.6667 | 1.3333 | 1.7778 | 10.6667 | N | O |  |  | 0 | 0 | 0 | 0 | 20 | 19.75 | 19.75 | 30.4167 | 30.4167 | 0 | 1 | 18 | 32 | EE | 2.3333 | 16.25 | 47.4167 | 18.5833 | 49.75 | 0 | 8 | 2 | 18 | 10 | 14 | I | L | 1
|  |  | 18 | 1 | R | SAND STAIN VARNISH | 2.5 | 3 | 4 | 3.0833 | 0.25 | 0.0625 | 3.0833 | Q |  |  |  | 0 | 0 | 0 | 0 | 23 | 30.4167 | 30.4167 | 33.5 | 33.5 | 0 | 1 | 19 | 17 | P | 1.1667 | 19.75 | 31.1667 | 20.9167 | 32.3333 | 0 | 9 | 0 | 19 | 10 | 33 | I | Z | 0
|  |  | 19 | 0 | S | LAY BATHROOM TILE | 2 | 2 | 3 | 2.1667 | 0.16667 | 0.027778 | 2.1667 | P |  |  |  | 0 | 0 | 0 | 0 | 24 | 20.9167 | 32.3333 | 23.0833 | 34.5 | 11.4167 | 0 | 20 | 18 | Q | 10.6667 | 19.75 | 19.75 | 30.4167 | 30.4167 | 1 | 9 | 1 | 20 | 11 | 15 | J | W | 0
|  |  | 20 | 1 | T | LAY COUNTERS | 1 | 1 | 1 | 1 | 0 | 0 | 1 | R |  |  |  | 0 | 0 | 0 | 0 | 26 | 33.5 | 33.5 | 34.5 | 34.5 | 0 | 1 | 21 | 30 | CC | 1 | 22.4167 | 43 | 23.4167 | 44 | 0 | 9 | 2 | 21 | 12 | 19 | O | P | 0
|  |  | 21 | 1 | U | INSTALL PLMB FXTRS | 1 | 1 | 1 | 1 | 0 | 0 | 1 | S | T |  |  | 0 | 0 | 0 | 0 | 27 | 34.5 | 34.5 | 35.5 | 35.5 | 0 | 1 | 22 | 34 | GG | 1.1667 | 22.4167 | 43 | 23.5833 | 44.1667 | 0 | 9 | 3 | 22 | 12 | 20 | O | Q | 0
|  |  | 22 | 1 | V | SAND PAINT INTER | 4 | 5 | 9 | 5.5 | 0.83333 | 0.69444 | 5.5 | U |  |  |  | 0 | 0 | 0 | 0 | 28 | 35.5 | 35.5 | 41 | 41 | 0 | 1 | 23 | 19 | R | 3.0833 | 30.4167 | 30.4167 | 33.5 | 33.5 | 1 | 10 | 0 | 23 | 13 | 16 | K | M | 0
|  |  | 23 | 0 | W | ATTACH GUTRS & DNSPT | 2 | 2 | 3 | 2.1667 | 0.16667 | 0.027778 | 2.1667 | J |  |  |  | 0 | 0 | 0 | 0 | 15 | 14.0833 | 45.25 | 16.25 | 47.4167 | 31.1667 | 0 | 24 | 20 | S | 2.1667 | 20.9167 | 32.3333 | 23.0833 | 34.5 | 0 | 10 | 1 | 24 | 14 | 17 | L | N | 1
|  |  | 24 | 1 | X | INSTALL KIT APPLNS | 1 | 1 | 1 | 1 | 0 | 0 | 1 | V |  |  |  | 0 | 0 | 0 | 0 | 29 | 41 | 41 | 42 | 42 | 0 | 1 | 25 | 35 | HH | 1.1667 | 23.5833 | 44.1667 | 24.75 | 45.3333 | 0 | 10 | 2 | 25 | 15 | 18 | W | EE | 0
|  |  | 25 | 1 | Y | INSTALL HOT WTR HTR | 1 | 1 | 1 | 1 | 0 | 0 | 1 | G | X |  |  | 0 | 0 | 0 | 0 | 32 | 42 | 42 | 43 | 43 | 0 | 1 | 26 | 21 | T | 1 | 33.5 | 33.5 | 34.5 | 34.5 | 1 | 11 | 0 | 26 | 16 | 21 | M | CC | 0
|  |  | 26 | 1 | Z | INSTALL FURN &AC | 0.5 | 1 | 1.5 | 1 | 0.16667 | 0.027778 | 1 | H | I | X |  | 0 | 0 | 0 | 0 | 33 | 42 | 42 | 43 | 43 | 0 | 1 | 27 | 22 | U | 1 | 34.5 | 34.5 | 35.5 | 35.5 | 1 | 12 | 0 | 27 | 16 | 22 | M | GG | 0
|  |  | 27 | 0 | AA | WALLPAPER | 1.5 | 2 | 3 | 2.0833 | 0.25 | 0.0625 | 2.0833 | V | X |  |  | 0 | 0 | 0 | 0 | 34 | 42 | 47.6667 | 44.0833 | 49.75 | 5.6667 | 0 | 28 | 23 | V | 5.5 | 35.5 | 35.5 | 41 | 41 | 1 | 13 | 0 | 28 | 17 | 19 | N | P | 0
|  |  | 28 | 1 | BB | INSTALL ELECT OUTLTS | 1 | 1 | 1 | 1 | 0 | 0 | 1 | Y | Z |  |  | 0 | 0 | 0 | 0 | 35 | 43 | 43 | 44 | 44 | 0 | 1 | 29 | 25 | X | 1 | 41 | 41 | 42 | 42 | 1 | 14 | 0 | 29 | 17 | 20 | N | Q | 1
|  |  | 29 | 0 | CC | PLACE INSUL IN ATTIC | 1 | 1 | 1 | 1 | 0 | 0 | 1 | M | N |  |  | 0 | 0 | 0 | 0 | 21 | 22.4167 | 43 | 23.4167 | 44 | 20.5833 | 0 | 30 | 31 | DD | 2 | 41 | 42 | 43 | 44 | 0 | 14 | 1 | 30 | 17 | 21 | N | CC | 0
|  |  | 30 | 0 | DD | LAY FLOORING | 1.5 | 2 | 2.5 | 2 | 0.16667 | 0.027778 | 2 | V |  |  |  | 0 | 0 | 0 | 0 | 30 | 41 | 42 | 43 | 44 | 1 | 0 | 31 | 37 | JJ | 1 | 41 | 48.75 | 42 | 49.75 | 0 | 14 | 2 | 31 | 18 | 42 | EE | End | 0
|  |  | 31 | 0 | EE | PAINT EXT TRIM | 2 | 2 | 4 | 2.3333 | 0.33333 | 0.11111 | 2.3333 | W |  |  |  | 0 | 0 | 0 | 0 | 18 | 16.25 | 47.4167 | 18.5833 | 49.75 | 31.1667 | 0 | 32 | 26 | Y | 1 | 42 | 42 | 43 | 43 | 1 | 15 | 0 | 32 | 19 | 24 | P | S | 0
|  |  | 32 | 1 | FF | CLEANUP | 1 | 1 | 3 | 1.3333 | 0.33333 | 0.11111 | 1.3333 | BB | CC | DD |  | 0 | 0 | 0 | 0 | 36 | 44 | 44 | 45.3333 | 45.3333 | 0 | 1 | 33 | 27 | Z | 1 | 42 | 42 | 43 | 43 | 1 | 15 | 1 | 33 | 20 | 23 | Q | R | 1
|  |  | 33 | 0 | GG | GRADE FRME WLKS DRV | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | M |  |  |  | 0 | 0 | 0 | 0 | 22 | 22.4167 | 43 | 23.5833 | 44.1667 | 20.5833 | 0 | 34 | 28 | AA | 2.0833 | 42 | 47.6667 | 44.0833 | 49.75 | 0 | 15 | 2 | 34 | 21 | 36 | CC | FF | 0
|  |  | 34 | 0 | HH | POUR WLKS DRIVE | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | GG |  |  |  | 0 | 0 | 0 | 0 | 25 | 23.5833 | 44.1667 | 24.75 | 45.3333 | 20.5833 | 0 | 35 | 29 | BB | 1 | 43 | 43 | 44 | 44 | 1 | 16 | 0 | 35 | 22 | 25 | GG | HH | 0
|  |  | 35 | 1 | II | FINISH GRADING | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | FF | HH |  |  | 0 | 0 | 0 | 0 | 38 | 45.3333 | 45.3333 | 46.5 | 46.5 | 0 | 1 | 36 | 33 | FF | 1.3333 | 44 | 44 | 45.3333 | 45.3333 | 1 | 17 | 0 | 36 | 23 | 26 | R | T | 1
|  |  | 36 | 0 | JJ | ATTACH CAB FXTRS | 1 | 1 | 1 | 1 | 0 | 0 | 1 | V |  |  |  | 0 | 0 | 0 | 0 | 31 | 41 | 48.75 | 42 | 49.75 | 7.75 | 0 | 37 | 38 | KK | 1 | 44 | 48.75 | 45 | 49.75 | 0 | 17 | 1 | 37 | 24 | 27 | S | U | 0
|  |  | 37 | 0 | KK | FINAL HOOKUP ELECT | 1 | 1 | 1 | 1 | 0 | 0 | 1 | BB |  |  |  | 0 | 0 | 0 | 0 | 37 | 44 | 48.75 | 45 | 49.75 | 4.75 | 0 | 38 | 36 | II | 1.1667 | 45.3333 | 45.3333 | 46.5 | 46.5 | 1 | 18 | 0 | 38 | 25 | 38 | HH | II | 0
|  |  | 38 | 0 | LL | LAY CARPETING | 1.5 | 2 | 2.5 | 2 | 0.16667 | 0.027778 | 2 | FF |  |  |  | 0 | 0 | 0 | 0 | 39 | 45.3333 | 47.75 | 47.3333 | 49.75 | 2.4167 | 0 | 39 | 39 | LL | 2 | 45.3333 | 47.75 | 47.3333 | 49.75 | 0 | 18 | 1 | 39 | 26 | 27 | T | U | 1
|  |  | 39 | 1 | MM | LANDSCAPE | 1.5 | 2 | 4 | 2.25 | 0.41667 | 0.17361 | 2.25 | II |  |  |  | 0 | 0 | 0 | 0 | 40 | 46.5 | 46.5 | 48.75 | 48.75 | 0 | 1 | 40 | 40 | MM | 2.25 | 46.5 | 46.5 | 48.75 | 48.75 | 1 | 19 | 0 | 40 | 27 | 28 | U | V | 1
|  |  | 40 | 1 | NN | FINISH CLOSE-OUT | 1 | 1 | 1 | 1 | 0 | 0 | 1 | MM |  |  |  | 0 | 0 | 0 | 0 | 41 | 48.75 | 48.75 | 49.75 | 49.75 | 0 | 1 | 41 | 41 | NN | 1 | 48.75 | 48.75 | 49.75 | 49.75 | 1 | 20 | 0 | 41 | 28 | 29 | V | X | 1
[29 empty] | 42 | 42 | End | 0 | 49.75 | 49.75 | 49.75 | 49.75 | 1 | 21 | 0 | 42 | 28 | 30 | V | DD | 0
[13 empty] | Num. Predecessors | 54 | [25 empty] | 43 | 28 | 31 | V | JJ | 0
[40 empty] | 44 | 28 | 34 | V | AA | 0
[40 empty] | 45 | 29 | 32 | X | Y | 1
[40 empty] | 46 | 29 | 33 | X | Z | 1
[40 empty] | 47 | 29 | 34 | X | AA | 0
[40 empty] | 48 | 30 | 36 | DD | FF | 0
[40 empty] | 49 | 31 | 42 | JJ | End | 0
[40 empty] | 50 | 32 | 35 | Y | BB | 1
[40 empty] | 51 | 33 | 35 | Z | BB | 1
[40 empty] | 52 | 34 | 42 | AA | End | 0
[40 empty] | 53 | 35 | 36 | BB | FF | 1
[40 empty] | 54 | 35 | 37 | BB | KK | 0
[40 empty] | 55 | 36 | 38 | FF | II | 1
[40 empty] | 56 | 36 | 39 | FF | LL | 0
[40 empty] | 57 | 37 | 42 | KK | End | 0
[40 empty] | 58 | 38 | 40 | II | MM | 1
[40 empty] | 59 | 39 | 42 | LL | End | 0
[40 empty] | 60 | 40 | 41 | MM | NN | 1
[40 empty] | 61 | 41 | 42 | NN | End | 1

## House_Schedule
Schedule House
|  | Search |  | Cash Flow
Bucket | 1 | DAYS |  | Activities
[9 empty] | Early | Late |  | Activity | Sched. | Sched. | Initial | Uniform | Final | Resources |  | Time
Project |  |  |  | Index | Sort | Name | Description | Time | Start | Start | Slack | Delay | Start | Finish | C.F. | C.F. | C.F. | Res. 1 | Color | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
Completion Time |  |  |  | 1 | 1 | Start | Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Max Delay | 0 | DAYS |  | 2 | 2 | A | OBTAIN BLDG PERMIT | 1.0833 | 0 | 0 | 0 | 0 | 0 | 1.0833 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay Unit Cost | 1 | /DAYS |  | 3 | 3 | B | CLEAR LOT & GRADE | 2.25 | 1.0833 | 1.0833 | 0 | 0 | 1.0833 | 3.3333 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earliest | 50.75 | DAYS |  | 4 | 4 | C | PLACE FORMS & RODS | 2.25 | 3.3333 | 3.3333 | 0 | 0 | 3.3333 | 5.5833 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled | 49.75 | DAYS |  | 5 | 5 | D | POUR SLAB | 1 | 5.5833 | 5.5833 | 0 | 0 | 5.5833 | 6.5833 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variance | Variance | 6 | 6 | E | ERECT WOODEN FRME | 5.3333 | 6.5833 | 6.5833 | 0 | 0 | 6.5833 | 11.9167 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resources | Avail. | Unit Cost | Cost | 7 | 7 | F | FASTEN SHEATH | 2.0833 | 11.9167 | 13.0833 | 1.1667 | 0 | 11.9167 | 14 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Res. 1 | 10 | 1 | 6200 | 8 | 8 | G | INSTALL RUF PLUMB | 3.1667 | 11.9167 | 12 | 0.083333 | 0 | 11.9167 | 15.0833 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 9 | 9 | H | INSTALL RUF WIRING | 2.3333 | 11.9167 | 12.8333 | 0.91667 | 0 | 11.9167 | 14.25 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Costs |  |  |  | 10 | 10 | I | INSTALL HVAC DUCTS | 3.25 | 11.9167 | 11.9167 | 0 | 0 | 11.9167 | 15.1667 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay | -1 |  |  | 11 | 11 | J | SHINGLE ROOF | 2.1667 | 11.9167 | 43.0833 | 31.1667 | 0 | 11.9167 | 14.0833 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variance | 6200 |  |  | 12 | 16 | O | RUF CARPENTRY | 5.3333 | 11.9167 | 14.4167 | 2.5 | 0 | 11.9167 | 17.25 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 6199 |  |  | 13 | 12 | K | COMPLETE EXT TRIM | 3.1667 | 14 | 34.5833 | 20.5833 | 0 | 14 | 17.1667 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 14 | 13 | L | INSULATE WALLS | 1.1667 | 15.1667 | 15.1667 | 0 | 0 | 15.1667 | 16.3333 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasibility |  |  |  | 15 | 24 | W | ATTACH GUTRS & DNSPT | 2.1667 | 14.0833 | 45.25 | 31.1667 | 0 | 14.0833 | 16.25 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Late | 0 |  |  | 16 | 14 | M | LAY BRICKWORK | 5.25 | 17.1667 | 37.75 | 20.5833 | 0 | 17.1667 | 22.4167 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule | 0 |  |  | 17 | 15 | N | SHEETROCK PLASTER | 3.4167 | 16.3333 | 16.3333 | 0 | 0 | 16.3333 | 19.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasible | TRUE |  |  | 18 | 32 | EE | PAINT EXT TRIM | 2.3333 | 16.25 | 47.4167 | 31.1667 | 0 | 16.25 | 18.5833 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 19 | 17 | P | INSTALL TUB & SHOWER | 1.1667 | 19.75 | 31.1667 | 11.4167 | 0 | 19.75 | 20.9167 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Flow |  |  |  | 20 | 18 | Q | FINISH CARPENTRY | 10.6667 | 19.75 | 19.75 | 0 | 0 | 19.75 | 30.4167 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest/DAYS | 1% |  |  | 21 | 30 | CC | PLACE INSUL IN ATTIC | 1 | 22.4167 | 43 | 20.5833 | 0 | 22.4167 | 23.4167 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest/Bucket | 1% |  |  | 22 | 34 | GG | GRADE FRME WLKS DRV | 1.1667 | 22.4167 | 43 | 20.5833 | 0 | 22.4167 | 23.5833 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Present Value | 0 |  |  | 23 | 19 | R | SAND STAIN VARNISH | 3.0833 | 30.4167 | 30.4167 | 0 | 0 | 30.4167 | 33.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uniform Value/DAYS | 0 |  |  | 24 | 20 | S | LAY BATHROOM TILE | 2.1667 | 20.9167 | 32.3333 | 11.4167 | 0 | 20.9167 | 23.0833 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 25 | 35 | HH | POUR WLKS DRIVE | 1.1667 | 23.5833 | 44.1667 | 20.5833 | 0 | 23.5833 | 24.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weighted Sum |  |  |  | 26 | 21 | T | LAY COUNTERS | 1 | 33.5 | 33.5 | 0 | 0 | 33.5 | 34.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Cost Weight | 50% |  |  | 27 | 22 | U | INSTALL PLMB FXTRS | 1 | 34.5 | 34.5 | 0 | 0 | 34.5 | 35.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Flow Weight | 50% |  |  | 28 | 23 | V | SAND PAINT INTER | 5.5 | 35.5 | 35.5 | 0 | 0 | 35.5 | 41 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weighted Sum | 3099.5 |  |  | 29 | 25 | X | INSTALL KIT APPLNS | 1 | 41 | 41 | 0 | 0 | 41 | 42 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 30 | 31 | DD | LAY FLOORING | 2 | 41 | 42 | 1 | 0 | 41 | 43 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 31 | 37 | JJ | ATTACH CAB FXTRS | 1 | 41 | 48.75 | 7.75 | 0 | 41 | 42 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 32 | 26 | Y | INSTALL HOT WTR HTR | 1 | 42 | 42 | 0 | 0 | 42 | 43 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 33 | 27 | Z | INSTALL FURN &AC | 1 | 42 | 42 | 0 | 0 | 42 | 43 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 34 | 28 | AA | WALLPAPER | 2.0833 | 42 | 47.6667 | 5.6667 | 0 | 42 | 44.0833 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 35 | 29 | BB | INSTALL ELECT OUTLTS | 1 | 43 | 43 | 0 | 0 | 43 | 44 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 36 | 33 | FF | CLEANUP | 1.3333 | 44 | 44 | 0 | 0 | 44 | 45.3333 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 37 | 38 | KK | FINAL HOOKUP ELECT | 1 | 44 | 48.75 | 4.75 | 0 | 44 | 45 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 38 | 36 | II | FINISH GRADING | 1.1667 | 45.3333 | 45.3333 | 0 | 0 | 45.3333 | 46.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 39 | 39 | LL | LAY CARPETING | 2 | 45.3333 | 47.75 | 2.4167 | 0 | 45.3333 | 47.3333 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 40 | 40 | MM | LANDSCAPE | 2.25 | 46.5 | 46.5 | 0 | 0 | 46.5 | 48.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 41 | 41 | NN | FINISH CLOSE-OUT | 1 | 48.75 | 48.75 | 0 | 0 | 48.75 | 49.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 42 | 42 | End | End | 0 | 49.75 | 49.75 | 0 | 0 | 49.75 | 49.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resources
[18 empty] | Used | Res. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Available | Res. 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
[18 empty] | Variance | Res. 1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
[18 empty] | Variance Unit Cost | Res. 1 | bar: Time 1 to Time 62
[18 empty] | Variance Cost | Res. 1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
[18 empty] | Cumulative Cash Flow |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
[18 empty] | Initial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Uniform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Final | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Bucket Cash Flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0